## README
Project | ConnectSphere Event Planning and Venue Booking System, IS212 (AY 2026/27 T1)
Version | 5, 11 September 2026
What changed in v5 | Closed eight open team assumptions (BDR section C). Two produced changes: registration lists now show name, email address and contact number rather than two fields (O-05), and a three-second response target for venue search, calendar load and registration submission was adopted and recorded in the Definition of Done (O-01, T-51). The other six confirmed existing assumptions. Six items remain open, all on stories outside Release 1. Story count and points are unchanged.
What changed in v4 | Applied the Week 4 customer clarifications (BDR C-55 to C-64). The sessions model was withdrawn: multi-session events are now set up as separate events (C-62), which rewrote 29 stories and retired ADR-004 and ADR-005. Tentative venue holding returned to Release 1 (C-60). Registration capacity is now governed by the booked venue's capacity, with manual VIP addition (C-58). Coordinator reassignment gained an acceptance step (C-56). Two previously logged backlog edits were applied (T-46, T-47/B-11).
Sheets | RELEASE 1 BACKLOG - the 47 stories in the first release, grouped by sprint. PRODUCT BACKLOG - the full 71-story candidate pool across 14 epics. SPRINT SUMMARY - counts and points per sprint, for velocity and burndown. CORE FEATURES BUILT - the 20 core features from the Week 4 instructions mapped to the stories that deliver them.
Backlog Decision Reference | Points to the Backlog Decision Review document, which holds all rationale. C- entries are customer clarifications from the Week 2 and Week 4 Q&A. T- entries are team decisions. O- entries are questions still open. B- entries are boundary rulings from the story overlap audit.
Where the reasoning lives | This workbook holds story data only. Every explanation of why a story exists, why a criterion is worded as it is, and which decisions remain assumptions rather than requirements is in the BDR.
Acceptance criteria | Given-When-Then scenarios first, each with a descriptive title, followed by a checklist distilled from them. The scenarios establish behaviour; the checklist maps onto test cases.
Estimation | T-shirt sizes set in planning poker. Points map S=1, M=3, L=5, XL=8 so velocity and burndown charts can be produced.
Editing | Add or change stories in the two backlog sheets. SPRINT SUMMARY recalculates from RELEASE 1 BACKLOG; do not overwrite its formulas. Record any new decision in the BDR and put its reference in the last column.

## RELEASE 1 BACKLOG
Sprint | Epic | Story ID | Story Title | User Story | Acceptance Criteria | Points | Backlog Decision Reference | Person Doing
Sprint 1 | E01 Access & Identity | E01-S01 | Log in to the system | As an Event Organiser, I want to log in with my registered credentials so that I can access my organisation's event information securely. | Scenario 1 - Valid credentials accepted Given I am a registered user with valid credentials When I submit my email address and password Then I am signed in and taken to the dashboard for my role Scenario 2 - Wrong password reveals nothing Given I am a registered user When I submit an incorrect password Then I remain signed out and see a message that does not reveal whether the email address is registered Scenario 3 - Lockout on fifth failure Given I have submitted 5 consecutive incorrect passwords When I attempt to sign in again Then my account is locked and I am shown how to reset my password Scenario 4 - Reset link issued Given my account is locked When I request a password reset Then a reset link is sent to my registered email address Scenario 5 - Lock lifted on new password Given I have followed a valid reset link When I set a new password Then the lock is lifted and I can sign in with the new password Checklist - Sign in with a valid email and password and reach the dashboard for my role - Be refused on an incorrect password without learning whether the email is registered - Be locked out on the 5th consecutive failed attempt - Receive a reset link at my registered email address - Regain access once the password has been reset - Have the lockout recorded in the activity log (E14-S02) | 3 | C-30, T-38, O-02 | xiang ying / ji ning
Sprint 1 | E01 Access & Identity | E01-S02 | Restrict event visibility to my own client | As an Event Organiser, I want to see only events belonging to my own client organisation so that other clients' information stays confidential. | Scenario 1 - Own client's events only Given I am signed in as an Event Organiser for Client A When I open my event list Then only events belonging to Client A are shown Scenario 2 - Direct access refused Given an event belongs to a client organisation I am not linked to When I navigate directly to that event's identifier Then access is refused and the attempt is recorded in the activity log Scenario 3 - Colleague's event visible Given my organisation has several Event Organisers When a colleague from my organisation creates an event Then I can see that event in my organisation's list Checklist - View only events linked to their own client organisation in their event list - Be denied access when attempting to open (e.g. via URL or ID) an event belonging to another client organisation - View events created by any Organiser within their own client organisation - Search for events without unrelated client organisations' events appearing in the results - Receive notifications that never reference events belonging to unrelated client organisations - Confirm that a denied access attempt is captured in the activity log with the user, event and time | 5 | C-40, B-01 | xiang ying / ji ning
Sprint 1 | E01 Access & Identity | E01-S03 | Hide internal planning information from Attendees | As an Attendee, I want to see only the published details of events I have registered for so that I am not shown ConnectSphere's internal planning information. | Scenario 1 - Published details only Given I am signed in as an Attendee and registered for an event When I view that event Then I see the published name, date, time and venue, and no Coordinator notes, booking decisions, equipment reservations or internal comments Scenario 2 - Internal screen refused Given I am signed in as an Attendee When I attempt to open an internal planning screen Then access is refused and the attempt is recorded in the activity log Checklist - View the published name, date, time and venue of an event I am registered for - Not see Coordinator notes, booking decisions, equipment reservations or comments - Be refused when opening an internal planning screen directly - Not see events or events I am not registered for | 3 | B-01 | xiang ying / ji ning
Sprint 1 | E01 Access & Identity | E01-S04 | Update my account details | As a system user, I want to update my name, organisation and contact details so that ConnectSphere reaches me at the correct address. | Scenario 1 - Valid changes saved Given I am signed in When I save valid changes to my profile Then the updated details are stored and shown when I next open my profile Scenario 2 - Malformed email rejected Given I enter an email address in an invalid format When I try to save Then the change is rejected and the invalid field is identified Scenario 3 - Duplicate email rejected Given I enter an email address already registered to another account When I try to save Then the change is rejected Scenario 4 - Notifications follow the new address Given I change my email address When the change is saved Then future notifications for my events are sent to the new address Checklist - Update name, organisation and contact details and see them persist - Be blocked from saving a malformed email address, with the field identified - Be blocked from taking an email address already in use - Receive subsequent notifications at the updated address - Not be able to change my own role from this screen | 1 | T-08 | xiang ying / ji ning
Sprint 1 | E01 Access & Identity | E01-S08 | Create an account | As an Attendee, I want to create an account so that I can register for events and manage my registrations. | Scenario 1 - Account created Given I do not have an account When I submit the required details Then an Attendee account is created and I can sign in with it Scenario 2 - Email already in use Given an account already exists with that email address When I submit the form Then I am told the address is already in use and no second account is created Scenario 3 - Invalid submission corrected Given required fields are missing or the password does not meet the stated policy When I submit Then the account is not created and I am shown what to correct Scenario 4 - Attendee role only Given I sign up through the public form When my account is created Then it holds the Attendee role only Checklist - Create an Attendee account with the required details and sign in with it - Be told the address is already in use when an account exists, with no second account created - Be shown what to correct when fields are missing or the password fails the policy - Receive only the Attendee role from the public sign-up form - Not be offered any internal role during sign-up | 3 | C-34, C-35, C-57 | xiang ying / ji ning
Sprint 1 | E01 Access & Identity | E01-S11 | Deactivate my account | As a system user, I want to deactivate my account so that I can stop using the system while ConnectSphere retains the records it needs. | Scenario 1 - Deactivated and signed out Given I am signed in When I confirm deactivation Then I am signed out and can no longer sign in with those credentials Scenario 2 - Historical records retained Given I have deactivated my account When ConnectSphere views an event I was linked to Then my past registrations and event records remain intact and attributed Scenario 3 - Upcoming registration released Given I am an Attendee registered for an upcoming event When I deactivate Then my registration is withdrawn and the place is released Scenario 4 - Coordinator with events blocked Given I am an Event Coordinator with events assigned to me When I attempt to deactivate Then deactivation is blocked until those events are reassigned Checklist - Deactivate my own account and be signed out immediately - Be unable to sign in afterwards - Have my historical event and registration records retained and still attributed - Have upcoming registrations released on deactivation (Attendees) - Be blocked from deactivating while I still hold assigned events (Coordinators) - Have the deactivation recorded in the activity log with actor and time | 3 | C-26, T-09 | xiang ying / ji ning
Sprint 1 | E02 Event Request & Submission | E02-S01 | Submit an event request | As an Event Organiser, I want to submit an event request so that ConnectSphere can begin planning my event. | Scenario 1 - Complete request submitted Given I am signed in as an Event Organiser and every mandatory field is complete When I submit the request Then its status becomes Submitted and I receive confirmation Scenario 2 - Missing mandatory fields blocked Given one or more mandatory fields are empty When I try to submit Then submission is blocked and every missing field is identified Scenario 3 - Past date blocked Given I enter a preferred date in the past When I try to submit Then submission is blocked with an explanation Scenario 4 - None required satisfies a field Given my event needs no equipment When I select 'none required' for that field Then the field counts as complete and submission proceeds Checklist - Enter all ten mandatory fields: event name, description, purpose, preferred dates and times, expected attendance, venue requirements, accessibility needs, equipment requirements, layout preference, registration setup - Be blocked from submitting while any mandatory field is empty, with each missing field named - Select 'none required' for equipment, layout or registration setup where the event does not need them - Be blocked from submitting a preferred date in the past - See the status change to Submitted and receive confirmation | 5 | C-36, T-11, T-12 | Aaron
Sprint 1 | E02 Event Request & Submission | E02-S02 | Save a draft event request | As an Event Organiser, I want to save an incomplete event request as a draft so that I can gather the missing information and complete it later. | Scenario 1 - Draft saved and hidden from Coordinators Given I have partially completed a request When I save it as a draft Then it is stored with status Draft and is not visible to Event Coordinators Scenario 2 - Draft reopened with values restored Given I have a saved draft When I reopen it Then all previously entered values are restored Scenario 3 - Draft deleted Given I have a draft I no longer need When I delete it Then it is removed from my list and is not counted as an active request Scenario 4 - Completed draft submitted Given a draft has every mandatory field complete When I submit it Then it follows E02-S01 and its status becomes Submitted Checklist - Save an event request without completing all mandatory fields - View all of my saved drafts, distinguishable from submitted requests - Reopen a draft and see previously entered values pre-filled - Continue editing a saved draft - Delete a draft I no longer need - Confirm that Event Coordinators cannot see my drafts | 3 | - | Aaron
Sprint 1 | E02 Event Request & Submission | E02-S03 | Match accessibility requirements to venue features | As an Event Organiser, I want to record the accessibility requirements for my event so that ConnectSphere only offers venues that can meet them. | Scenario 1 - Predefined requirements stored Given I am creating an event request When I select one or more accessibility requirements from the predefined list Then they are stored with the request and shown to the assigned Event Coordinator Scenario 2 - Free-text captured but not matched Given my requirement is not in the predefined list When I enter it in the free-text box Then it is stored and shown to the Coordinator, and is excluded from automated venue matching Scenario 3 - Search filters on predefined requirements Given predefined accessibility requirements are recorded for an event When a venue search is run for the event Then venues that do not meet them are excluded or clearly marked unsuitable Checklist - Select one or more accessibility requirements from the predefined list - Enter an additional requirement in a free-text box - See the free-text entry passed to the Coordinator but not used for automated matching - Confirm that predefined requirements filter the venue search results | 1 | T-13, T-45, B-06 | Aaron
Sprint 1 | E05 Venue Catalogue & Availability | E05-S01 | Maintain the venue catalogue | As a Venue Staff member, I want to add and update venue records so that Event Coordinators search against accurate information. | Scenario 1 - Venue added and searchable Given I am adding a venue When I save it with location, capacity, facilities, accessibility features, supported layouts and operating hours Then it becomes searchable by Event Coordinators Scenario 2 - Capacity drop flags bookings Given a venue has confirmed bookings When I reduce its capacity below the expected attendance of one of those bookings Then the affected bookings are flagged for review and the assigned Coordinators are notified Scenario 3 - Venue retired Given a venue has no future bookings When I retire it Then it no longer appears in search results and its past bookings are retained Scenario 4 - Retirement blocked by future bookings Given a venue has future bookings When I attempt to retire it Then retirement is blocked and the blocking bookings are identified Checklist - Add a venue with location, capacity, facilities, accessibility features, supported layouts and operating hours - Update any of those attributes on an existing venue - Confirm a new venue becomes searchable by Event Coordinators - Confirm affected bookings are flagged when capacity drops below a booked attendance - Retire a venue that has no future bookings - Be blocked from retiring a venue with future bookings, with those bookings identified | 3 | T-13, T-18, B-05 | Le Xin
Sprint 1 | E05 Venue Catalogue & Availability | E05-S02 | Match layout requirements to venue capacity | As a Venue Staff member, I want to record the room layouts supported by a venue and the maximum capacity for each layout, so that Event Coordinators only consider arrangements the venue can accommodate. | Scenario 1 - Layout and capacity stored Given I am editing a venue When I add a supported layout with its maximum capacity Then it is stored against that venue Scenario 2 - Undersized layout excluded Given an event requires a theatre layout for a given attendance When a Coordinator searches for venues Then venues whose theatre capacity is below that attendance are excluded or marked unsuitable Scenario 3 - Duplicate layout warned Given a layout already exists on the venue When I try to add it again Then I am warned and no duplicate is created Checklist - View the layouts supported by a venue and their maximum capacities - Add one or more room layouts to a venue - Set and edit a maximum capacity for each layout - Remove a layout no longer offered at the venue - Be warned when adding a layout that already exists | 3 | T-45, B-07 | Le Xin
Sprint 1 | E14 Audit & History | E14-S02 | Record significant actions in an activity log | As a ConnectSphere staff member, I want significant actions to be recorded so that we can determine who did what and when. | Scenario 1 - Status change recorded Given an event status changes When the change completes Then an entry is recorded with the actor, the action, the affected event and the time Scenario 2 - Access denial recorded Given a user is denied access to an event or screen When the refusal occurs Then an entry is recorded with the user, the target and the time Scenario 3 - Booking decision recorded Given a venue booking is approved, rejected or released When the action completes Then an entry is recorded with the actor, the action, the affected records and the time Scenario 4 - Deactivation recorded Given an account is deactivated When the action completes Then an entry is recorded Scenario 5 - Log entries immutable Given an activity log entry exists When any user attempts to edit or delete it Then the attempt is refused Checklist - Record every event status change with actor, action, event and time - Record every denied access attempt with user, target and time - Record every venue booking approval, rejection and release - Record every account deactivation - Confirm log entries cannot be edited or deleted by any user | 3 | T-04 | Le Xin
Sprint 2 | E03 Review, Coordination & Status | E03-S01 | Assign an Event Coordinator to a request | As an Event Organiser, I want my submitted request to be assigned an Event Coordinator automatically so that my event has one clear internal owner from the outset. | Scenario 1 - Exactly one Coordinator assigned Given a request is submitted When submission completes Then the system assigns exactly one Event Coordinator, the status becomes Under Review, and that Coordinator is notified Scenario 2 - Fewest active events wins Given several Event Coordinators are available When the system assigns one Then it selects the Coordinator with the fewest active events Scenario 3 - Reassignment requested Given I am the assigned Coordinator and a reassignment has been agreed offline When I request reassignment to a named colleague Then the request is recorded, that colleague is notified, and I remain assigned until they accept Scenario 4 - Reassignment accepted Given a reassignment request is awaiting my acceptance When I accept it Then I become the assigned Coordinator, the previous assignment ends, and the change is recorded in the activity log Scenario 5 - Reassignment declined Given a reassignment request is awaiting acceptance When the named colleague declines it Then the original Coordinator remains assigned and is notified of the refusal Scenario 6 - Unassigned Coordinator refused Given I am not the assigned Coordinator When I attempt to reassign the event Then the action is refused Checklist - Confirm that exactly one Event Coordinator is assigned on submission - Confirm the assigned Coordinator is the one with the fewest active events - Confirm the status moves from Submitted to Under Review - Request reassignment to a named colleague as the assigned Coordinator - Confirm the original Coordinator stays assigned until the colleague accepts - Accept a reassignment request and take ownership of the event - Decline a reassignment request, leaving the original Coordinator assigned - Be refused when attempting to reassign an event assigned to someone else | 3 | C-12, C-41, C-55, C-56, T-14, T-15
Sprint 2 | E03 Review, Coordination & Status | E03-S02 | Request clarification from the Event Organiser | As an Event Coordinator, I want to return a request to the Event Organiser with specific questions so that unclear requirements are corrected before planning begins. | Scenario 1 - Questions sent, status changes Given I am reviewing a request with status Under Review When I record my questions and send them Then the status becomes Awaiting Clarification and the Event Organiser is notified with the questions Scenario 2 - Organiser responds, review resumes Given a request is Awaiting Clarification When the Event Organiser responds and resubmits Then the status returns to Under Review and I am notified Scenario 3 - Outstanding questions visible Given a request is Awaiting Clarification When I view it Then the outstanding questions and the date they were raised are shown Checklist - Record one or more questions against a request under review - Confirm the status becomes Awaiting Clarification and the Organiser is notified - See the outstanding questions and the date raised on the event record - Confirm the status returns to Under Review when the Organiser responds - Filter my events by clarification status | 3 | C-10, B-02
Sprint 2 | E03 Review, Coordination & Status | E03-S03 | Decide on an event request | As an Event Coordinator, I want to approve or reject a request and record my reasoning so that the Event Organiser receives a clear, traceable decision. | Scenario 1 - Approved to planning Given a request has status Under Review and the required information is complete When I approve it Then the status becomes Approved and the Event Organiser is notified Scenario 2 - Incomplete request blocked Given required information is still incomplete When I try to approve the request Then approval is blocked and the missing items are listed Scenario 3 - Rejected with reason Given a request is under review When I reject it and record a reason Then the status becomes Rejected, the reason is stored and the Event Organiser is notified Scenario 4 - Rejection without reason blocked Given I attempt to reject without recording a reason When I confirm Then the rejection is blocked Scenario 5 - Rejected record is read-only Given a request has been rejected When the Event Organiser views it Then the reason and the date of the decision are shown and the request is read-only Checklist - Approve a request whose required information is complete - Confirm an approval sets the status to Approved and notifies the Organiser - Be blocked from approving an incomplete request, with the missing items listed - Reject a request under review with a recorded reason - Be blocked from rejecting without a recorded reason - Confirm a rejection sets the status to Rejected and notifies the Organiser - See the reason and decision date in plain language as the Organiser - Confirm a rejected request is read-only | 3 | C-09, T-39, T-41, T-43, O-06
Sprint 2 | E03 Review, Coordination & Status | E03-S05 | Track the status of my event | As an Event Organiser, I want to see the current status of my event so that I know what stage planning has reached without contacting my Coordinator. | Scenario 1 - Current status in plain language Given my event is at any stage When I open it Then the current status and the date it was reached are shown in plain language Scenario 2 - New status and history entry Given my event's status changes When I next open the event Then the new status is shown and the change appears in the event history Checklist - See the current status in plain language - See the date the current status was reached - See the new status when the event reaches a new stage - See the full status history for my event, drawn from the activity log (E14-S02) | 1 | B-03
Sprint 2 | E03 Review, Coordination & Status | E03-S06 | Discuss an event through comments | As an Event Organiser, I want to post comments and questions on my event record so that planning conversations with my Coordinator are kept with the event rather than scattered across email. | Scenario 1 - Comment posted and Coordinator notified Given I have access to an event When I post a comment Then it appears on the event with my name and the time it was posted, and the assigned Coordinator is notified Scenario 2 - Comments in chronological order Given a comment exists on my event When I view the event Then all comments are shown in chronological order Scenario 3 - Comment on inaccessible event refused Given I do not have access to an event When I attempt to post a comment Then the action is refused Checklist - Post a comment on an event I have access to - See my name and the posting time against each comment - See all comments in chronological order - Confirm the assigned Coordinator is notified of a new comment - Be refused when posting on an event I cannot access | 3 | C-15, C-47, B-02
Sprint 2 | E03 Review, Coordination & Status | E03-S07 | View and update event information | As an Event Coordinator, I want to view and update event information while planning is underway so that the record stays accurate as details are settled. | Scenario 1 - Organiser edits before approval Given an event has not yet been approved When the Event Organiser edits any field Then the change is saved directly against the event Scenario 2 - Coordinator edits after approval Given an event has been approved When I edit any field as the assigned Coordinator Then the change is saved and recorded in the activity log Scenario 3 - Organiser edits unrestricted fields Given an event has been approved When the Event Organiser edits the event name, description, purpose or registration dates Then the change is saved directly Scenario 4 - Restricted edit routed to change request Given an event has been approved When the Event Organiser attempts to change the date, time, expected attendance, venue requirements, accessibility needs, equipment requirements or layout Then direct editing is refused and they are directed to raise a change request (E10-S01) Scenario 5 - Unassigned Coordinator refused Given I am not the assigned Coordinator When I attempt to edit an approved event Then the action is refused Checklist - Edit any field as the Organiser while the event is Draft, Submitted, Under Review or Awaiting Clarification - Edit any field as the assigned Coordinator once the event is Approved or later - Edit name, description, purpose and registration dates as the Organiser after approval - Be refused as the Organiser when directly editing date, time, attendance, venue requirements, accessibility needs, equipment requirements or layout after approval - Be redirected to the change request flow (E10-S01) when a restricted edit is attempted - Confirm every post-approval edit is recorded in the activity log | 5 | C-52, T-16
Sprint 2 | E05 Venue Catalogue & Availability | E05-S03 | View the venue availability calendar | As an Event Coordinator, I want to view a venue's calendar so that I can see when the venue is free, pending, confirmed or blocked. | Scenario 1 - Four states distinguishable Given a venue has bookings and blocks in a period When I open its calendar for that period Then each entry is shown as Free, Tentative, Confirmed or Blocked, and the states are visually distinguishable Scenario 2 - Other events' details withheld Given I do not have permission to view another event's details When I open the calendar Then the period is shown as unavailable without revealing the other event's information Scenario 3 - Block distinct from booking Given a venue is blocked for maintenance When I view the calendar Then the block is clearly distinct from a booking Checklist - Select a date or date range to view venue availability - See the availability state for each period: Free, Tentative, Confirmed or Blocked - See the event name, event, date and time for periods I am permitted to view - Navigate to different dates or date ranges - See a blocked venue clearly distinguished from a booked one - See periods I cannot view marked unavailable without any event detail | 5 | C-40, C-60, T-17, T-49
Sprint 2 | E05 Venue Catalogue & Availability | E05-S04 | Block a venue for maintenance | As a Venue Staff member, I want to block a venue for maintenance, renovation or safety reasons so that it is not offered for events during that period. | Scenario 1 - Free period blocked Given a venue has no bookings in a period When I block that period and record a reason Then the venue no longer appears as available for those dates Scenario 2 - Block over a confirmed booking warned Given a venue already has a confirmed booking in the period When I try to block it Then I am warned of the conflict and must resolve it before the block takes effect Scenario 3 - Affected Coordinators notified Given a block is created over an upcoming event's dates When the block is saved Then the affected Coordinators are notified Checklist - Block a venue for a specified period with a recorded reason - Be prevented from finalising a block that overlaps a confirmed booking, with the conflicting booking identified - Remove or shorten an existing block, restoring availability for the released period - Confirm a blocked venue no longer appears as available during the blocked period - Confirm affected Event Coordinators are notified when a block affects an upcoming event | 3 | -
Sprint 2 | E06 Venue Search & Booking | E06-S01 | Search for suitable venues | As an Event Coordinator, I want to search venues by date, time, attendance, capacity, layout, accessibility and facilities so that I can shortlist options for an event quickly. | Scenario 1 - Matching venues listed Given venues exist that match all my criteria and are available When I run the search Then those venues are listed with their capacity, layouts and facilities Scenario 2 - Near matches show failing criteria Given no venue matches all criteria When I run the search Then near matches are returned rather than an empty result Scenario 3 - Undersized venue marked unsuitable Given a venue is available but its capacity is below the event's expected attendance When results are displayed Then it is excluded or clearly marked as unsuitable Scenario 4 - Blocked or booked venues excluded Given a venue is blocked or already confirmed the event's period When I run the search Then it does not appear as available Checklist - Search by date, time, expected attendance, location, capacity, accessibility, layout and required facilities - See matching venues with their capacity, layouts and facilities - See near matches returned rather than an empty result when nothing matches fully - Confirm venues below the event's attendance are excluded or marked unsuitable - Confirm blocked or already-confirmed venues do not appear as available - Apply several filters together in one search | 5 | B-08
Sprint 2 | E11 Notifications & Reminders | E11-S01 | Notify users about events they are involved in | As a user involved in an event, I want to be notified when its status or arrangements change so that I do not have to keep checking the system and nobody continues working from outdated information. | Scenario 1 - Status change notified Given I am linked to an event When its status changes or a booking decision is made Then I receive a notification stating what changed, when, and which event it concerns Scenario 2 - All affected parties notified Given the event's date, time or venue changes When the change takes effect Then the Event Organiser, assigned Venue Staff, assigned Technical Support Staff and registered Attendees are all notified Scenario 3 - Unaffected users not notified Given a change does not affect a particular user's responsibilities When the change occurs Then that user is not notified Scenario 4 - Delivered in-app and by email Given a notification is generated for me When it is delivered Then it appears in the system and is also sent to my registered email address Scenario 5 - Unread notifications distinguished Given I have several unread notifications When I open my notification list Then they are shown newest first with unread ones distinguished Scenario 6 - Marked as read Given I open an unread notification When I have read it Then it is marked as read Checklist - Receive a notification when an event I am linked to changes status - Receive a notification when a booking decision is made - Confirm all affected parties are notified when the event's date, time or venue changes - Confirm users whose responsibilities are unaffected are not notified - See what changed, when, and which event and event it concerns - Receive the same notification in the system and by email - See notifications newest first with unread ones distinguished - Mark a notification as read | 5 | C-04, C-29, C-53, T-35, T-36, T-44, T-48
Sprint 3 | E06 Venue Search & Booking | E06-S02 | Check venue suitability against event requirements | As an Event Coordinator, I want the system to compare a venue against the event's recorded requirements so that I do not request a venue that cannot meet them. | Scenario 1 - Suitability shown for the event Given an event has recorded requirements When I view a venue in the context of the event Then a suitability status is shown for the event Scenario 2 - Failing requirements named Given a venue fails one or more recorded requirements When I view it Then it is marked unsuitable and every failing requirement is named Scenario 3 - All requirements met Given a venue meets all recorded requirements for the event When I view it Then it is marked suitable Scenario 4 - Unsuitable venue may still be requested Given a venue is marked unsuitable When I submit a booking request for it anyway Then the request is accepted and the unsuitability is shown to the Venue Staff for their decision Checklist - View a suitability status for a venue against a specific event - See the venue marked unsuitable when it fails one or more recorded requirements - See every failing requirement named - See the venue marked suitable when it meets all recorded requirements - Confirm suitability is advisory and does not itself block a booking request | 3 | C-06, T-13, T-21, B-08
Sprint 3 | E06 Venue Search & Booking | E06-S03 | Request a venue booking | As an Event Coordinator, I want to submit a venue booking request for an event so that Venue Staff can review it and decide whether the venue can be provided. | Scenario 1 - Request created as Pending Given an event has recorded requirements and no pending request When I submit a booking request for a venue Then the request is created with status Pending, the venue calendar shows the period as Tentative, and the Venue Staff are notified Scenario 2 - First request moves event to Planning Given the event has status Approved When the first booking request for any of its events is submitted Then the event status becomes Planning Scenario 3 - Second request for same event blocked Given the event already has a pending booking request When I submit another for the same event Then submission is blocked and the existing pending request is identified Scenario 4 - Venue taken by another event blocked Given a venue is already Pending or Confirmed for another event over the same period When I submit a request for it Then submission is blocked and the conflict is explained Checklist - Submit a booking request for an event using its recorded requirements - Confirm the request is created as Pending and Venue Staff are notified - Confirm the venue calendar shows the period as Tentative - Confirm the event status moves from Approved to Planning on the first request - Be blocked from holding more than one pending request for the same event - Be blocked from requesting a venue already Pending or Confirmed for another event in that period - View the status of each of my booking requests | 3 | C-01, C-16, C-17, C-37, C-46, C-60, T-20, T-49
Sprint 3 | E06 Venue Search & Booking | E06-S04 | Decide on a venue booking request | As a Venue Staff member, I want to approve or reject booking requests and record my reasoning so that Coordinators receive a clear, traceable decision. | Scenario 1 - Request approved and confirmed Given a booking request is pending and the venue is free for the period When I approve it Then the booking becomes Confirmed, the venue calendar is updated and the Coordinator is notified Scenario 2 - Rejected with reason and alternative Given I reject a request When I record a reason and optionally suggest an alternative venue Then the Coordinator is notified with both, and can amend the request to the suggested alternative without restarting the search Scenario 3 - Rejection without reason blocked Given I attempt to reject without recording a reason When I confirm Then the rejection is blocked Checklist - Approve a pending booking request for a free venue - Confirm the booking becomes Confirmed and the calendar updates - Reject a request with a recorded reason - Be blocked from rejecting without a reason - Suggest an alternative venue alongside a rejection - Confirm the Coordinator can amend the request to the suggested venue without starting a new search - Confirm the Coordinator is notified of either decision | 3 | C-08, T-39
Sprint 3 | E06 Venue Search & Booking | E06-S05 | Hold a venue tentatively | As an Event Coordinator, I want to place a tentative hold on a venue so that it is not taken by another event while the arrangements are still being finalised. | Scenario 1 - Tentative hold placed Given a venue is free for the period When I place a tentative hold Then the calendar shows the period as Tentative and the hold is recorded against my event Scenario 2 - Slot already held or booked Given a venue already has a tentative hold or a confirmed booking for the period When I attempt to hold it for another event Then the hold is refused and the existing hold or booking is identified Scenario 3 - Hold becomes a booking request Given I hold a venue tentatively When I submit a booking request for that venue Then the hold becomes a pending booking request for the same period Scenario 4 - Hold released Given I hold a venue tentatively and no longer need it When I release the hold Then the period returns to Free on the calendar Checklist - Place a tentative hold on a venue that is free for the period - See the period shown as Tentative on the venue calendar - Be refused when the slot already has a tentative hold or a confirmed booking for another event - Convert a tentative hold into a booking request - Release a tentative hold, returning the period to Free - Confirm only one active hold or confirmed booking exists per venue and period | 3 | C-01, C-16, C-37, C-60, T-49
Sprint 3 | E06 Venue Search & Booking | E06-S06 | Prevent double-booking of a venue | As a Venue Staff member, I want to be blocked from approving a booking that overlaps an existing confirmed booking for the same venue so that a venue is never committed to two events at once. | Scenario 1 - Overlapping approval blocked Given a venue has a confirmed booking When I attempt to approve another request overlapping that period Then approval is blocked and the conflicting booking is identified Scenario 2 - Competing request flagged Given two pending requests cover the same venue and overlapping times When I approve one of them Then the other is flagged as conflicting and cannot be approved until the conflict is resolved Scenario 3 - Simultaneous approval fails safely Given another Venue Staff member approves a conflicting request moments before me When my approval is processed Then it fails and I am told the venue has just been taken Checklist - Be blocked from approving a request overlapping an existing confirmed booking - See which existing booking is causing the conflict - Confirm a competing pending request is flagged as conflicting once one is approved - Confirm a simultaneous approval by another Venue Staff member fails safely - Be told the venue has been taken when a simultaneous approval wins - Confirm no venue ever holds two confirmed bookings over the same period | 5 | C-46, T-22
Sprint 3 | E07 Equipment & Technical Support | E07-S01 | Maintain the equipment catalogue | As a Technical Support Staff member, I want to maintain equipment records including type, quantity, location and operational status so that availability checks are based on accurate data. | Scenario 1 - Item added and reservable Given I am adding an equipment item When I save its type, description, quantity, location and operational status Then it becomes available for reservation Scenario 2 - Quantity drop flags reservations Given an item is already reserved for upcoming events When I reduce its quantity below the amount reserved Then the affected reservations are flagged and the relevant Coordinators are notified Scenario 3 - Item retired Given an item has no future reservations When I retire it Then it no longer appears in availability checks and its past reservations are retained Checklist - Add an equipment item with type, description, quantity, location and operational status - Update any of those attributes on an existing item - Confirm a new item becomes available for reservation - Confirm affected reservations are flagged when quantity drops below the amount reserved - Retire an item that has no future reservations - Confirm retired items no longer appear in availability checks | 3 | -
Sprint 3 | E07 Equipment & Technical Support | E07-S02 | Request equipment for an event | As an Event Coordinator, I want to record the equipment an event needs, with quantities, so that Technical Support Staff can check whether it can be provided. | Scenario 1 - Equipment recorded against an event Given I am planning an approved event When I add equipment items with quantities to an event Then the request is saved against the event and the Technical Support Staff are notified Scenario 2 - Request exceeds total stock Given I request more of an item than ConnectSphere owns in total When I save the request Then I am warned that the request cannot be met from existing stock Scenario 3 - Events independent of each other Given an event has several events When I record equipment for the event Then the other events are unaffected Checklist - Add equipment items with quantities to a specific event - Confirm the request is saved against the event and Technical Support Staff are notified - Be warned when requesting more than ConnectSphere owns in total - Record different equipment for different events of the same event - Amend or remove an equipment request before it is reserved | 3 | T-25
Sprint 3 | E07 Equipment & Technical Support | E07-S03 | Check equipment availability | As a Technical Support Staff member, I want to see how much of an item is free for a given date and time so that I can decide whether a request can be met. | Scenario 1 - Reserved and faulty stock excluded Given some items are reserved for other events in the period When I check availability Then the free quantity excludes those reservations and any items marked damaged or under maintenance Scenario 2 - Location does not affect availability Given an item is free for the requested date and time but is currently located at another venue When I check availability Then it is shown as available and no transport allowance is applied Scenario 3 - Non-overlapping events share an item Given two events require the same item at non-overlapping times on the same day When I check availability Then the item is free for both Checklist - View the free quantity of an item for a given date and time - Confirm reservations for other events are excluded from the free quantity - Confirm damaged or under-maintenance items are excluded - Confirm items at other venues are still counted as available - Confirm the same item can serve two events at non-overlapping times | 5 | C-07, C-20
Sprint 3 | E07 Equipment & Technical Support | E07-S04 | Reserve equipment for an event | As a Technical Support Staff member, I want to reserve equipment for an event so that limited equipment is not committed to two events at the same time. | Scenario 1 - Full reservation recorded Given sufficient equipment is free for the period When I reserve the requested quantity Then the reservation is recorded against the event and the Event Coordinator is notified Scenario 2 - Partial reservation and shortfall Given only part of the requested quantity is free When I record a partial reservation Then the Coordinator is notified of the shortfall and the outstanding quantity Scenario 3 - Fully committed item shows nothing free Given an item becomes fully committed When availability is next checked for that period Then no free quantity is shown Scenario 4 - Reservation released Given an event is cancelled or its equipment is no longer required When I release the reservation Then the quantity returns to the available pool Checklist - Select an event and equipment item to reserve - Specify the quantity required - See an error when the requested quantity exceeds what is available - Record a partial reservation and notify the Coordinator of the shortfall - Release a reservation when an event is cancelled or the equipment is no longer needed - Receive confirmation showing the event, date, time, item and quantity | 5 | C-21, T-24, B-09
Sprint 3 | E07 Equipment & Technical Support | E07-S05 | Mark equipment as unavailable | As a Technical Support Staff member, I want to mark equipment as damaged or under maintenance so that it is not treated as available for events. | Scenario 1 - Item marked unavailable Given an item has no reservations in the period When I mark it unavailable with a reason and a period Then it is excluded from availability checks for that period Scenario 2 - Reserved item flags its events Given an item is reserved for an upcoming event When I mark it unavailable Then the affected events are flagged and their Coordinators are notified Checklist - Mark an item unavailable for a specified period with a recorded reason - Confirm it is excluded from availability checks for that period - Confirm affected events are flagged and Coordinators notified - Return an item to service, restoring it to availability checks | 1 | B-04
Sprint 3 | E07 Equipment & Technical Support | E07-S06 | Request technical support for an event | As an Event Coordinator, I want to request on-site technical support for an event and describe what is needed so that suitable staff can be allocated. | Scenario 1 - Support request recorded Given an event requires technical support When I submit a request describing the support and the times it is needed Then the Technical Support Staff are notified and the request is recorded against the event Scenario 2 - Request accepted before venue confirmed Given the event does not yet have a confirmed venue When I submit a technical support request Then it is accepted and reviewed alongside venue identification Scenario 3 - Event marked as needing none Given an event needs no technical support When I mark it as such Then no request is created and confirmation is not blocked on staff assignment Checklist - Submit a technical support request against a specific event - Describe the support required and the times it is needed - Confirm Technical Support Staff are notified - Submit a request before the venue is confirmed - Mark an event as requiring no technical support | 1 | C-22, T-23
Sprint 3 | E07 Equipment & Technical Support | E07-S07 | Assign and manage technical staff for an event | As a Technical Support Staff member, I want to assign and manage available colleagues to support an event so that the right people are on site at the right time. | Scenario 1 - Available colleague assigned Given an event has an open technical support request and a colleague is available for its times When I assign them Then they are notified and the assignment appears on their schedule Scenario 2 - Overlapping assignment blocked Given a colleague is already assigned to another event at an overlapping time When I try to assign them Then the assignment is blocked and the conflicting event is identified Scenario 3 - Assignment removed Given an assignment exists When I remove it Then the colleague is notified and the slot is freed Scenario 4 - Replacement assigned under same check Given I have removed an assignment When I assign a replacement Then the same conflict check is applied Checklist - Assign a colleague only when they have no conflicting assignment the event's period - See the assignment on the assigned staff member's schedule - Be blocked from assigning a colleague with an overlapping assignment, with the conflicting event identified - Remove an existing assignment - Assign a replacement colleague subject to the same conflict check - Confirm the staff member is notified when assigned or removed | 3 | C-39
Sprint 3 | E08 Readiness & Confirmation | E08-S03 | Confirm an event | As an Event Coordinator, I want to confirm an event once the event's arrangements are complete so that the Event Organiser and Attendees can rely on the details. | Scenario 1 - All arrangements complete, event confirmed Given the event has a confirmed venue booking and its full requested equipment reserved When I confirm the event Then the status becomes Confirmed and the Event Organiser is notified with the confirmed details Scenario 2 - Missing venue blocks confirmation Given the event has no confirmed venue When I try to confirm Then confirmation is blocked and the outstanding items are listed Scenario 3 - Partial equipment blocks confirmation Given the event has only a partial equipment reservation When I try to confirm Then confirmation is blocked and the outstanding quantity is shown Scenario 4 - None required does not block Given the event was submitted with 'none required' for equipment When I confirm it Then that requirement counts as fulfilled and does not block confirmation Scenario 5 - Outstanding support assignment blocks confirmation Given the event requested technical support and no staff are assigned When I try to confirm Then confirmation is blocked Scenario 6 - Organiser sees confirmed arrangements Given an event has been confirmed When the Event Organiser views it Then the confirmed venue, date, time and arrangements are shown Checklist - Confirm an event that has a confirmed venue and full equipment reservation - Be blocked from confirming while the event lacks a venue - Be blocked from confirming while an equipment reservation is partial, with the shortfall shown - Confirm an event whose equipment requirement was recorded as 'none required' - Be blocked from confirming while a requested technical support assignment is outstanding - Confirm the Event Organiser is notified with the full confirmed details | 5 | C-13, C-39, C-59, C-63, T-02, T-24, T-27
Sprint 4 | E08 Readiness & Confirmation | E08-S04 | Revert a confirmed event to planning | As an Event Coordinator, I want to return a confirmed event to planning when an arrangement breaks so that its status reflects reality. | Scenario 1 - Reverted with a recorded reason Given an event is Confirmed When I revert it to Planning and record a reason Then the status becomes Planning and the Event Organiser is notified with the reason Scenario 2 - Registered Attendees notified Given registered Attendees exist When the event is reverted Then they are notified that arrangements are being revised Scenario 3 - No automatic reversion Given an arrangement breaks on a confirmed event When no one reverts it Then the status stays Confirmed and the affected arrangement is flagged Checklist - Revert a confirmed event to Planning with a recorded reason - Confirm the Organiser is notified with the reason - Confirm registered Attendees are notified - Confirm the status never reverts automatically - Confirm the reversion is recorded in the activity log | 1 | C-48, T-03, T-28
Sprint 4 | E08 Readiness & Confirmation | E08-S05 | Complete an event | As an Event Coordinator, I want an event to become Completed once it has taken place so that attendance can be recorded and the event closed. | Scenario 1 - Auto-completed after the end time Given an event is Confirmed and its end time has passed When the system next evaluates it Then the status becomes Completed Scenario 2 - Marked complete manually Given an event is Confirmed and has already started When I mark it complete Then the status becomes Completed Scenario 3 - Premature completion blocked Given an event is Confirmed and has not yet started When I try to mark it complete Then the action is blocked Scenario 4 - Cancelled event never auto-completes Given an event is Cancelled When its original end time passes Then it is not auto-completed and remains Cancelled Checklist - Confirm an event auto-completes once its end time has passed - Mark an event complete manually once it has started - Be blocked from marking an event complete before it has started - Confirm a cancelled event is never auto-completed - Confirm the transition is recorded in the activity log | 3 | T-03, T-26, T-48
Sprint 4 | E09 Attendee Registration | E09-S01 | Register for an event | As an Attendee, I want to register for a confirmed event so that my place is reserved and I receive the event information. | Scenario 1 - Place reserved in an open event Given an event is Confirmed, registration is open and places remain When I submit the required registration information Then my place is reserved and I receive a confirmation containing the event details Scenario 2 - Duplicate registration prevented Given I have already registered for the event When I try to register again Then I am told I am already registered and no duplicate registration is created Scenario 3 - Missing fields identified Given a required registration field is empty When I submit Then registration is blocked and the missing fields are identified Scenario 4 - Unconfirmed event refused Given an event is not Confirmed When I attempt to register Then registration is refused Checklist - Register for a confirmed event - Provide name, email address and contact number as the required registration information - Receive a confirmation containing the event details - Be told I am already registered rather than creating a duplicate - Be blocked with missing fields identified when required information is absent - Be refused registration for an event that is not Confirmed | 5 | C-35, T-48
Sprint 4 | E09 Attendee Registration | E09-S02 | Enforce registration capacity | As an Event Organiser, I want registration to stop at the booked venue's capacity so that more people do not register than the venue can hold. | Scenario 1 - Venue capacity enforced Given the event's capacity is the booked venue's capacity When registrations reach that number Then further registrations are refused Scenario 2 - Simultaneous final registration Given one place remains When two Attendees submit registrations at the same moment Then only one succeeds and the other is told the event is full Scenario 3 - Full event offers the waiting list Given the event is full When an Attendee opens the registration page Then registration is closed and the waiting list is offered where it is enabled Scenario 4 - VIP added beyond normal registration Given normal registration is full and total registrations remain below the booked venue's capacity When the Event Coordinator adds a VIP attendee manually Then the registration is created and recorded as a manual addition Scenario 5 - VIP blocked at venue capacity Given total registrations already equal the booked venue's capacity When the Event Coordinator attempts to add a VIP manually Then the addition is blocked Checklist - Confirm registration is refused once the booked venue's capacity is reached - Confirm a simultaneous final registration is handled without over-booking - Confirm the waiting list is offered when the event is full and the list is enabled - Add a VIP attendee manually when normal registration is full - Be blocked from adding a VIP once total registrations equal venue capacity - Confirm a manual addition is distinguishable from a normal registration | 3 | C-05, C-58, T-30, T-31, T-50, B-11
Sprint 4 | E09 Attendee Registration | E09-S03 | Control the registration period | As an Event Organiser, I want to set when registration opens and closes, and when withdrawal closes, so that Attendees can act only during the permitted windows. | Scenario 1 - Before registration opens Given the registration opening date has not been reached When an Attendee views the event Then registration is shown as not yet open and the opening date is stated Scenario 2 - After registration closes Given the registration closing date has passed When an Attendee tries to register Then registration is refused Scenario 3 - Closing date after event start warned Given I set a closing date that falls after the event has started When I save Then I am warned and asked to confirm this is intended Scenario 4 - Waiting list enabled Given I enable the waiting list for an event When an event becomes full Then Attendees are offered the waiting list Checklist - Set registration opening and closing dates - Set a withdrawal deadline - Enable or disable the waiting list for the event - Confirm registration is refused outside the permitted window - Confirm the opening date is shown to Attendees before registration opens - Be warned when setting a closing date after the event has started | 3 | C-24, C-44, T-42
Sprint 4 | E09 Attendee Registration | E09-S04 | Join the waiting list | As an Attendee, I want to join the waiting list when an event is full so that I can still attend if a place is released. | Scenario 1 - Joined a full event's list Given an event is full and the waiting list is enabled When I join the waiting list Then I am added and told I will be notified when a place is released Scenario 2 - Released place notified to all Given a place is released in an event with a waiting list When the place becomes available Then all waitlisted Attendees are notified and the place is claimed on a first-come, first-served basis Scenario 3 - Claimed place leaves the list Given I claim a released place When my registration completes Then I am removed from the waiting list Scenario 4 - Disabled list offers nothing Given the waiting list is disabled for an event When the event is full Then no waiting list is offered Checklist - Join the waiting list for a full event where the list is enabled - See confirmation that I have joined - Receive a notification when a place is released - Claim a released place on a first-come, first-served basis - Leave the waiting list - Confirm no waiting list is offered when the Organiser has disabled it | 5 | C-23, T-33, T-46, B-10
Sprint 4 | E09 Attendee Registration | E09-S05 | Withdraw my registration | As an Attendee, I want to withdraw my registration so that my place is released to someone else. | Scenario 1 - Registration withdrawn Given I am registered and the withdrawal deadline has not passed When I withdraw Then my registration is cancelled and the place becomes available again Scenario 2 - Withdrawal after deadline refused Given the withdrawal deadline has passed When I try to withdraw Then I am told withdrawal has closed and given a contact for assistance Checklist - Withdraw my registration before the deadline - Confirm the released place becomes available again - Be refused after the withdrawal deadline, with a contact provided | 3 | C-24, T-48, B-10
Sprint 4 | E09 Attendee Registration | E09-S06 | Record attendance | As an Event Coordinator, I want to record which registered Attendees actually attended the event so that registration and attendance can be distinguished. | Scenario 1 - Attendance marked after completion Given an event has status Completed When I mark an Attendee as attended for an event Then their record shows attended and the registration figure is unchanged Scenario 2 - Registered but not attended Given a registered Attendee did not attend When the event is Completed Then they are shown as registered but not attended Scenario 3 - Recording before completion blocked Given an event is not yet Completed When I try to record attendance Then the action is blocked Checklist - Mark a registered Attendee as attended for a specific event - Confirm the registration figure is unchanged by attendance recording - See Attendees who registered but did not attend distinguished from those who did - Be blocked from recording attendance before the event is Completed - View registration and attendance counts side by side for the event | 3 | C-45
Sprint 4 | E09 Attendee Registration | E09-S07 | View registrations for my event | As an Event Organiser, I want to view the list of Attendees registered for my event so that I can plan for the numbers attending the event. | Scenario 1 - Registrations grouped by event Given Attendees have registered for my event When I open its registration list Then I see each Attendee's name, email address and contact number Scenario 2 - Counts and remaining capacity Given I open the registration list When it is displayed Then the registered count and remaining capacity are shown for the event Scenario 3 - Unmanaged event refused Given an event does not belong to my client organisation When I attempt to open its registration list Then access is refused Scenario 4 - Waitlist shown separately Given a waiting list exists for an event When I view the list Then waitlisted Attendees are shown separately from registered Attendees Checklist - View registered Attendees for an event I manage, grouped by event - See each Attendee's name, email address and contact number, and no other personal data - See registered count and remaining capacity for the event - See waitlisted Attendees separately from registered ones - Be refused access to registration lists for events I do not manage | 1 | C-26, T-32, O-05
Sprint 4 | E10 Changes, Rescheduling & Cancellation | E10-S01 | Request a change after submission | As an Event Organiser, I want to request a change to my event after it has been submitted or confirmed so that the arrangements reflect what I now need. | Scenario 1 - Change request recorded Given my event has been approved or confirmed When I submit a change request describing what should change Then the assigned Coordinator is notified and the request is recorded against the event Scenario 2 - Confirmed details shown alongside Given a change request is pending When I view my event Then the currently confirmed details are still shown alongside the pending request Scenario 3 - Refused edit offers the form Given I attempt to edit a restricted field directly after approval When the edit is refused Then I am offered the change request form pre-filled with that field Scenario 4 - Approved change applied Given the Coordinator approves my change request When it is applied Then the event is updated and I am notified Checklist - Submit a change request against an approved or confirmed event - Describe the change requested - Confirm the assigned Coordinator is notified - See currently confirmed details alongside any pending request - Reach the change request form when a restricted direct edit is refused - Be notified when the Coordinator approves or declines the request | 3 | C-14, C-52, C-54, T-16
Sprint 4 | E10 Changes, Rescheduling & Cancellation | E10-S02 | Distinguish minor edits from arrangement-affecting changes | As an Event Coordinator, I want the system to tell me when a change affects arrangements already confirmed so that I re-check them rather than assuming they still hold. | Scenario 1 - Attendance beyond capacity flagged Given an event has a confirmed venue When its expected attendance is increased beyond that venue's capacity Then the venue booking is flagged for review and the Venue Staff are notified Scenario 2 - Description-only edit flags nothing Given an event has a confirmed venue and equipment When only the event description is edited Then no arrangements are flagged Scenario 3 - Affected arrangements shown first Given a change affects confirmed arrangements When I save it Then I am shown which arrangements are affected before the change takes effect Scenario 4 - Over-subscription warns only Given a venue change reduces the event's capacity below its registration count When the change is saved Then I am warned and shown the over-subscription, and no Attendee is automatically removed or waitlisted Scenario 5 - Date change flags venue and equipment Given the event's date or time changes When the change takes effect Then its venue booking and equipment reservations are flagged as requiring reconfirmation Checklist - Confirm attendance increases beyond venue capacity flag the booking for review - Confirm description-only edits flag nothing - See which arrangements are affected before a change takes effect - Confirm over-subscription warns the Coordinator without removing Attendees - Confirm date or time changes flag both venue and equipment for reconfirmation - Confirm affected Venue Staff and Technical Support Staff are notified | 5 | C-05, T-16, B-05, B-11
Sprint 4 | E10 Changes, Rescheduling & Cancellation | E10-S04 | Cancel an event | As an Event Coordinator, I want to cancel an event and release its arrangements so that venues and equipment do not stay committed to something that will not happen. | Scenario 1 - Event cancelled, arrangements released Given an Event Organiser requests cancellation When I cancel the event and record a reason Then its status becomes Cancelled, its venue booking and equipment reservations are released, the venue calendar is updated and the affected staff are notified Scenario 2 - Attendees and waitlist notified Given Attendees are registered or waitlisted for a cancelled event When the cancellation completes Then all of them are notified Scenario 3 - Cancelled event read-only Given an event has been cancelled When any user views it Then it is read-only and shows the cancellation reason and date Scenario 4 - Organiser cancellation becomes a request Given an Event Organiser attempts to cancel directly When they submit Then the action is recorded as a cancellation request for the Coordinator to action Checklist - Cancel an event, releasing its venue and equipment - Record a reason for the cancellation - Confirm the released venue becomes available again on the calendar - Confirm released equipment returns to the available pool - Confirm registered and waitlisted Attendees are notified - Confirm a cancelled event is read-only and shows its reason and date | 5 | C-14, C-54, T-07, T-48

## PRODUCT BACKLOG
Release | Epic | Story ID | Story Title | User Story | Acceptance Criteria | Points | Backlog Decision Reference
1 | E01 Access & Identity | E01-S01 | Log in to the system | As an Event Organiser, I want to log in with my registered credentials so that I can access my organisation's event information securely. | Scenario 1 - Valid credentials accepted Given I am a registered user with valid credentials When I submit my email address and password Then I am signed in and taken to the dashboard for my role Scenario 2 - Wrong password reveals nothing Given I am a registered user When I submit an incorrect password Then I remain signed out and see a message that does not reveal whether the email address is registered Scenario 3 - Lockout on fifth failure Given I have submitted 5 consecutive incorrect passwords When I attempt to sign in again Then my account is locked and I am shown how to reset my password Scenario 4 - Reset link issued Given my account is locked When I request a password reset Then a reset link is sent to my registered email address Scenario 5 - Lock lifted on new password Given I have followed a valid reset link When I set a new password Then the lock is lifted and I can sign in with the new password Checklist - Sign in with a valid email and password and reach the dashboard for my role - Be refused on an incorrect password without learning whether the email is registered - Be locked out on the 5th consecutive failed attempt - Receive a reset link at my registered email address - Regain access once the password has been reset - Have the lockout recorded in the activity log (E14-S02) | 3 | C-30, T-38, O-02
1 | E01 Access & Identity | E01-S02 | Restrict event visibility to my own client | As an Event Organiser, I want to see only events belonging to my own client organisation so that other clients' information stays confidential. | Scenario 1 - Own client's events only Given I am signed in as an Event Organiser for Client A When I open my event list Then only events belonging to Client A are shown Scenario 2 - Direct access refused Given an event belongs to a client organisation I am not linked to When I navigate directly to that event's identifier Then access is refused and the attempt is recorded in the activity log Scenario 3 - Colleague's event visible Given my organisation has several Event Organisers When a colleague from my organisation creates an event Then I can see that event in my organisation's list Checklist - View only events linked to their own client organisation in their event list - Be denied access when attempting to open (e.g. via URL or ID) an event belonging to another client organisation - View events created by any Organiser within their own client organisation - Search for events without unrelated client organisations' events appearing in the results - Receive notifications that never reference events belonging to unrelated client organisations - Confirm that a denied access attempt is captured in the activity log with the user, event and time | 5 | C-40, B-01
1 | E01 Access & Identity | E01-S03 | Hide internal planning information from Attendees | As an Attendee, I want to see only the published details of events I have registered for so that I am not shown ConnectSphere's internal planning information. | Scenario 1 - Published details only Given I am signed in as an Attendee and registered for an event When I view that event Then I see the published name, date, time and venue, and no Coordinator notes, booking decisions, equipment reservations or internal comments Scenario 2 - Internal screen refused Given I am signed in as an Attendee When I attempt to open an internal planning screen Then access is refused and the attempt is recorded in the activity log Checklist - View the published name, date, time and venue of an event I am registered for - Not see Coordinator notes, booking decisions, equipment reservations or comments - Be refused when opening an internal planning screen directly - Not see events or events I am not registered for | 3 | B-01
1 | E01 Access & Identity | E01-S04 | Update my account details | As a system user, I want to update my name, organisation and contact details so that ConnectSphere reaches me at the correct address. | Scenario 1 - Valid changes saved Given I am signed in When I save valid changes to my profile Then the updated details are stored and shown when I next open my profile Scenario 2 - Malformed email rejected Given I enter an email address in an invalid format When I try to save Then the change is rejected and the invalid field is identified Scenario 3 - Duplicate email rejected Given I enter an email address already registered to another account When I try to save Then the change is rejected Scenario 4 - Notifications follow the new address Given I change my email address When the change is saved Then future notifications for my events are sent to the new address Checklist - Update name, organisation and contact details and see them persist - Be blocked from saving a malformed email address, with the field identified - Be blocked from taking an email address already in use - Receive subsequent notifications at the updated address - Not be able to change my own role from this screen | 1 | T-08
1 | E01 Access & Identity | E01-S08 | Create an account | As an Attendee, I want to create an account so that I can register for events and manage my registrations. | Scenario 1 - Account created Given I do not have an account When I submit the required details Then an Attendee account is created and I can sign in with it Scenario 2 - Email already in use Given an account already exists with that email address When I submit the form Then I am told the address is already in use and no second account is created Scenario 3 - Invalid submission corrected Given required fields are missing or the password does not meet the stated policy When I submit Then the account is not created and I am shown what to correct Scenario 4 - Attendee role only Given I sign up through the public form When my account is created Then it holds the Attendee role only Checklist - Create an Attendee account with the required details and sign in with it - Be told the address is already in use when an account exists, with no second account created - Be shown what to correct when fields are missing or the password fails the policy - Receive only the Attendee role from the public sign-up form - Not be offered any internal role during sign-up | 3 | C-34, C-35, C-57
1 | E01 Access & Identity | E01-S11 | Deactivate my account | As a system user, I want to deactivate my account so that I can stop using the system while ConnectSphere retains the records it needs. | Scenario 1 - Deactivated and signed out Given I am signed in When I confirm deactivation Then I am signed out and can no longer sign in with those credentials Scenario 2 - Historical records retained Given I have deactivated my account When ConnectSphere views an event I was linked to Then my past registrations and event records remain intact and attributed Scenario 3 - Upcoming registration released Given I am an Attendee registered for an upcoming event When I deactivate Then my registration is withdrawn and the place is released Scenario 4 - Coordinator with events blocked Given I am an Event Coordinator with events assigned to me When I attempt to deactivate Then deactivation is blocked until those events are reassigned Checklist - Deactivate my own account and be signed out immediately - Be unable to sign in afterwards - Have my historical event and registration records retained and still attributed - Have upcoming registrations released on deactivation (Attendees) - Be blocked from deactivating while I still hold assigned events (Coordinators) - Have the deactivation recorded in the activity log with actor and time | 3 | C-26, T-09
1 | E02 Event Request & Submission | E02-S01 | Submit an event request | As an Event Organiser, I want to submit an event request so that ConnectSphere can begin planning my event. | Scenario 1 - Complete request submitted Given I am signed in as an Event Organiser and every mandatory field is complete When I submit the request Then its status becomes Submitted and I receive confirmation Scenario 2 - Missing mandatory fields blocked Given one or more mandatory fields are empty When I try to submit Then submission is blocked and every missing field is identified Scenario 3 - Past date blocked Given I enter a preferred date in the past When I try to submit Then submission is blocked with an explanation Scenario 4 - None required satisfies a field Given my event needs no equipment When I select 'none required' for that field Then the field counts as complete and submission proceeds Checklist - Enter all ten mandatory fields: event name, description, purpose, preferred dates and times, expected attendance, venue requirements, accessibility needs, equipment requirements, layout preference, registration setup - Be blocked from submitting while any mandatory field is empty, with each missing field named - Select 'none required' for equipment, layout or registration setup where the event does not need them - Be blocked from submitting a preferred date in the past - See the status change to Submitted and receive confirmation | 5 | C-36, T-11, T-12
1 | E02 Event Request & Submission | E02-S02 | Save a draft event request | As an Event Organiser, I want to save an incomplete event request as a draft so that I can gather the missing information and complete it later. | Scenario 1 - Draft saved and hidden from Coordinators Given I have partially completed a request When I save it as a draft Then it is stored with status Draft and is not visible to Event Coordinators Scenario 2 - Draft reopened with values restored Given I have a saved draft When I reopen it Then all previously entered values are restored Scenario 3 - Draft deleted Given I have a draft I no longer need When I delete it Then it is removed from my list and is not counted as an active request Scenario 4 - Completed draft submitted Given a draft has every mandatory field complete When I submit it Then it follows E02-S01 and its status becomes Submitted Checklist - Save an event request without completing all mandatory fields - View all of my saved drafts, distinguishable from submitted requests - Reopen a draft and see previously entered values pre-filled - Continue editing a saved draft - Delete a draft I no longer need - Confirm that Event Coordinators cannot see my drafts | 3 | -
1 | E02 Event Request & Submission | E02-S03 | Match accessibility requirements to venue features | As an Event Organiser, I want to record the accessibility requirements for my event so that ConnectSphere only offers venues that can meet them. | Scenario 1 - Predefined requirements stored Given I am creating an event request When I select one or more accessibility requirements from the predefined list Then they are stored with the request and shown to the assigned Event Coordinator Scenario 2 - Free-text captured but not matched Given my requirement is not in the predefined list When I enter it in the free-text box Then it is stored and shown to the Coordinator, and is excluded from automated venue matching Scenario 3 - Search filters on predefined requirements Given predefined accessibility requirements are recorded for an event When a venue search is run for the event Then venues that do not meet them are excluded or clearly marked unsuitable Checklist - Select one or more accessibility requirements from the predefined list - Enter an additional requirement in a free-text box - See the free-text entry passed to the Coordinator but not used for automated matching - Confirm that predefined requirements filter the venue search results | 1 | T-13, T-45, B-06
1 | E03 Review, Coordination & Status | E03-S01 | Assign an Event Coordinator to a request | As an Event Organiser, I want my submitted request to be assigned an Event Coordinator automatically so that my event has one clear internal owner from the outset. | Scenario 1 - Exactly one Coordinator assigned Given a request is submitted When submission completes Then the system assigns exactly one Event Coordinator, the status becomes Under Review, and that Coordinator is notified Scenario 2 - Fewest active events wins Given several Event Coordinators are available When the system assigns one Then it selects the Coordinator with the fewest active events Scenario 3 - Reassignment requested Given I am the assigned Coordinator and a reassignment has been agreed offline When I request reassignment to a named colleague Then the request is recorded, that colleague is notified, and I remain assigned until they accept Scenario 4 - Reassignment accepted Given a reassignment request is awaiting my acceptance When I accept it Then I become the assigned Coordinator, the previous assignment ends, and the change is recorded in the activity log Scenario 5 - Reassignment declined Given a reassignment request is awaiting acceptance When the named colleague declines it Then the original Coordinator remains assigned and is notified of the refusal Scenario 6 - Unassigned Coordinator refused Given I am not the assigned Coordinator When I attempt to reassign the event Then the action is refused Checklist - Confirm that exactly one Event Coordinator is assigned on submission - Confirm the assigned Coordinator is the one with the fewest active events - Confirm the status moves from Submitted to Under Review - Request reassignment to a named colleague as the assigned Coordinator - Confirm the original Coordinator stays assigned until the colleague accepts - Accept a reassignment request and take ownership of the event - Decline a reassignment request, leaving the original Coordinator assigned - Be refused when attempting to reassign an event assigned to someone else | 3 | C-12, C-41, C-55, C-56, T-14, T-15
1 | E03 Review, Coordination & Status | E03-S02 | Request clarification from the Event Organiser | As an Event Coordinator, I want to return a request to the Event Organiser with specific questions so that unclear requirements are corrected before planning begins. | Scenario 1 - Questions sent, status changes Given I am reviewing a request with status Under Review When I record my questions and send them Then the status becomes Awaiting Clarification and the Event Organiser is notified with the questions Scenario 2 - Organiser responds, review resumes Given a request is Awaiting Clarification When the Event Organiser responds and resubmits Then the status returns to Under Review and I am notified Scenario 3 - Outstanding questions visible Given a request is Awaiting Clarification When I view it Then the outstanding questions and the date they were raised are shown Checklist - Record one or more questions against a request under review - Confirm the status becomes Awaiting Clarification and the Organiser is notified - See the outstanding questions and the date raised on the event record - Confirm the status returns to Under Review when the Organiser responds - Filter my events by clarification status | 3 | C-10, B-02
1 | E03 Review, Coordination & Status | E03-S03 | Decide on an event request | As an Event Coordinator, I want to approve or reject a request and record my reasoning so that the Event Organiser receives a clear, traceable decision. | Scenario 1 - Approved to planning Given a request has status Under Review and the required information is complete When I approve it Then the status becomes Approved and the Event Organiser is notified Scenario 2 - Incomplete request blocked Given required information is still incomplete When I try to approve the request Then approval is blocked and the missing items are listed Scenario 3 - Rejected with reason Given a request is under review When I reject it and record a reason Then the status becomes Rejected, the reason is stored and the Event Organiser is notified Scenario 4 - Rejection without reason blocked Given I attempt to reject without recording a reason When I confirm Then the rejection is blocked Scenario 5 - Rejected record is read-only Given a request has been rejected When the Event Organiser views it Then the reason and the date of the decision are shown and the request is read-only Checklist - Approve a request whose required information is complete - Confirm an approval sets the status to Approved and notifies the Organiser - Be blocked from approving an incomplete request, with the missing items listed - Reject a request under review with a recorded reason - Be blocked from rejecting without a recorded reason - Confirm a rejection sets the status to Rejected and notifies the Organiser - See the reason and decision date in plain language as the Organiser - Confirm a rejected request is read-only | 3 | C-09, T-39, T-41, T-43, O-06
1 | E03 Review, Coordination & Status | E03-S05 | Track the status of my event | As an Event Organiser, I want to see the current status of my event so that I know what stage planning has reached without contacting my Coordinator. | Scenario 1 - Current status in plain language Given my event is at any stage When I open it Then the current status and the date it was reached are shown in plain language Scenario 2 - New status and history entry Given my event's status changes When I next open the event Then the new status is shown and the change appears in the event history Checklist - See the current status in plain language - See the date the current status was reached - See the new status when the event reaches a new stage - See the full status history for my event, drawn from the activity log (E14-S02) | 1 | B-03
1 | E03 Review, Coordination & Status | E03-S06 | Discuss an event through comments | As an Event Organiser, I want to post comments and questions on my event record so that planning conversations with my Coordinator are kept with the event rather than scattered across email. | Scenario 1 - Comment posted and Coordinator notified Given I have access to an event When I post a comment Then it appears on the event with my name and the time it was posted, and the assigned Coordinator is notified Scenario 2 - Comments in chronological order Given a comment exists on my event When I view the event Then all comments are shown in chronological order Scenario 3 - Comment on inaccessible event refused Given I do not have access to an event When I attempt to post a comment Then the action is refused Checklist - Post a comment on an event I have access to - See my name and the posting time against each comment - See all comments in chronological order - Confirm the assigned Coordinator is notified of a new comment - Be refused when posting on an event I cannot access | 3 | C-15, C-47, B-02
1 | E03 Review, Coordination & Status | E03-S07 | View and update event information | As an Event Coordinator, I want to view and update event information while planning is underway so that the record stays accurate as details are settled. | Scenario 1 - Organiser edits before approval Given an event has not yet been approved When the Event Organiser edits any field Then the change is saved directly against the event Scenario 2 - Coordinator edits after approval Given an event has been approved When I edit any field as the assigned Coordinator Then the change is saved and recorded in the activity log Scenario 3 - Organiser edits unrestricted fields Given an event has been approved When the Event Organiser edits the event name, description, purpose or registration dates Then the change is saved directly Scenario 4 - Restricted edit routed to change request Given an event has been approved When the Event Organiser attempts to change the date, time, expected attendance, venue requirements, accessibility needs, equipment requirements or layout Then direct editing is refused and they are directed to raise a change request (E10-S01) Scenario 5 - Unassigned Coordinator refused Given I am not the assigned Coordinator When I attempt to edit an approved event Then the action is refused Checklist - Edit any field as the Organiser while the event is Draft, Submitted, Under Review or Awaiting Clarification - Edit any field as the assigned Coordinator once the event is Approved or later - Edit name, description, purpose and registration dates as the Organiser after approval - Be refused as the Organiser when directly editing date, time, attendance, venue requirements, accessibility needs, equipment requirements or layout after approval - Be redirected to the change request flow (E10-S01) when a restricted edit is attempted - Confirm every post-approval edit is recorded in the activity log | 5 | C-52, T-16
1 | E05 Venue Catalogue & Availability | E05-S01 | Maintain the venue catalogue | As a Venue Staff member, I want to add and update venue records so that Event Coordinators search against accurate information. | Scenario 1 - Venue added and searchable Given I am adding a venue When I save it with location, capacity, facilities, accessibility features, supported layouts and operating hours Then it becomes searchable by Event Coordinators Scenario 2 - Capacity drop flags bookings Given a venue has confirmed bookings When I reduce its capacity below the expected attendance of one of those bookings Then the affected bookings are flagged for review and the assigned Coordinators are notified Scenario 3 - Venue retired Given a venue has no future bookings When I retire it Then it no longer appears in search results and its past bookings are retained Scenario 4 - Retirement blocked by future bookings Given a venue has future bookings When I attempt to retire it Then retirement is blocked and the blocking bookings are identified Checklist - Add a venue with location, capacity, facilities, accessibility features, supported layouts and operating hours - Update any of those attributes on an existing venue - Confirm a new venue becomes searchable by Event Coordinators - Confirm affected bookings are flagged when capacity drops below a booked attendance - Retire a venue that has no future bookings - Be blocked from retiring a venue with future bookings, with those bookings identified | 3 | T-13, T-18, B-05
1 | E05 Venue Catalogue & Availability | E05-S02 | Match layout requirements to venue capacity | As a Venue Staff member, I want to record the room layouts supported by a venue and the maximum capacity for each layout, so that Event Coordinators only consider arrangements the venue can accommodate. | Scenario 1 - Layout and capacity stored Given I am editing a venue When I add a supported layout with its maximum capacity Then it is stored against that venue Scenario 2 - Undersized layout excluded Given an event requires a theatre layout for a given attendance When a Coordinator searches for venues Then venues whose theatre capacity is below that attendance are excluded or marked unsuitable Scenario 3 - Duplicate layout warned Given a layout already exists on the venue When I try to add it again Then I am warned and no duplicate is created Checklist - View the layouts supported by a venue and their maximum capacities - Add one or more room layouts to a venue - Set and edit a maximum capacity for each layout - Remove a layout no longer offered at the venue - Be warned when adding a layout that already exists | 3 | T-45, B-07
1 | E05 Venue Catalogue & Availability | E05-S03 | View the venue availability calendar | As an Event Coordinator, I want to view a venue's calendar so that I can see when the venue is free, pending, confirmed or blocked. | Scenario 1 - Four states distinguishable Given a venue has bookings and blocks in a period When I open its calendar for that period Then each entry is shown as Free, Tentative, Confirmed or Blocked, and the states are visually distinguishable Scenario 2 - Other events' details withheld Given I do not have permission to view another event's details When I open the calendar Then the period is shown as unavailable without revealing the other event's information Scenario 3 - Block distinct from booking Given a venue is blocked for maintenance When I view the calendar Then the block is clearly distinct from a booking Checklist - Select a date or date range to view venue availability - See the availability state for each period: Free, Tentative, Confirmed or Blocked - See the event name, event, date and time for periods I am permitted to view - Navigate to different dates or date ranges - See a blocked venue clearly distinguished from a booked one - See periods I cannot view marked unavailable without any event detail | 5 | C-40, C-60, T-17, T-49
1 | E05 Venue Catalogue & Availability | E05-S04 | Block a venue for maintenance | As a Venue Staff member, I want to block a venue for maintenance, renovation or safety reasons so that it is not offered for events during that period. | Scenario 1 - Free period blocked Given a venue has no bookings in a period When I block that period and record a reason Then the venue no longer appears as available for those dates Scenario 2 - Block over a confirmed booking warned Given a venue already has a confirmed booking in the period When I try to block it Then I am warned of the conflict and must resolve it before the block takes effect Scenario 3 - Affected Coordinators notified Given a block is created over an upcoming event's dates When the block is saved Then the affected Coordinators are notified Checklist - Block a venue for a specified period with a recorded reason - Be prevented from finalising a block that overlaps a confirmed booking, with the conflicting booking identified - Remove or shorten an existing block, restoring availability for the released period - Confirm a blocked venue no longer appears as available during the blocked period - Confirm affected Event Coordinators are notified when a block affects an upcoming event | 3 | -
1 | E06 Venue Search & Booking | E06-S01 | Search for suitable venues | As an Event Coordinator, I want to search venues by date, time, attendance, capacity, layout, accessibility and facilities so that I can shortlist options for an event quickly. | Scenario 1 - Matching venues listed Given venues exist that match all my criteria and are available When I run the search Then those venues are listed with their capacity, layouts and facilities Scenario 2 - Near matches show failing criteria Given no venue matches all criteria When I run the search Then near matches are returned rather than an empty result Scenario 3 - Undersized venue marked unsuitable Given a venue is available but its capacity is below the event's expected attendance When results are displayed Then it is excluded or clearly marked as unsuitable Scenario 4 - Blocked or booked venues excluded Given a venue is blocked or already confirmed the event's period When I run the search Then it does not appear as available Checklist - Search by date, time, expected attendance, location, capacity, accessibility, layout and required facilities - See matching venues with their capacity, layouts and facilities - See near matches returned rather than an empty result when nothing matches fully - Confirm venues below the event's attendance are excluded or marked unsuitable - Confirm blocked or already-confirmed venues do not appear as available - Apply several filters together in one search | 5 | B-08
1 | E06 Venue Search & Booking | E06-S02 | Check venue suitability against event requirements | As an Event Coordinator, I want the system to compare a venue against the event's recorded requirements so that I do not request a venue that cannot meet them. | Scenario 1 - Suitability shown for the event Given an event has recorded requirements When I view a venue in the context of the event Then a suitability status is shown for the event Scenario 2 - Failing requirements named Given a venue fails one or more recorded requirements When I view it Then it is marked unsuitable and every failing requirement is named Scenario 3 - All requirements met Given a venue meets all recorded requirements for the event When I view it Then it is marked suitable Scenario 4 - Unsuitable venue may still be requested Given a venue is marked unsuitable When I submit a booking request for it anyway Then the request is accepted and the unsuitability is shown to the Venue Staff for their decision Checklist - View a suitability status for a venue against a specific event - See the venue marked unsuitable when it fails one or more recorded requirements - See every failing requirement named - See the venue marked suitable when it meets all recorded requirements - Confirm suitability is advisory and does not itself block a booking request | 3 | C-06, T-13, T-21, B-08
1 | E06 Venue Search & Booking | E06-S03 | Request a venue booking | As an Event Coordinator, I want to submit a venue booking request for an event so that Venue Staff can review it and decide whether the venue can be provided. | Scenario 1 - Request created as Pending Given an event has recorded requirements and no pending request When I submit a booking request for a venue Then the request is created with status Pending, the venue calendar shows the period as Tentative, and the Venue Staff are notified Scenario 2 - First request moves event to Planning Given the event has status Approved When the first booking request for any of its events is submitted Then the event status becomes Planning Scenario 3 - Second request for same event blocked Given the event already has a pending booking request When I submit another for the same event Then submission is blocked and the existing pending request is identified Scenario 4 - Venue taken by another event blocked Given a venue is already Pending or Confirmed for another event over the same period When I submit a request for it Then submission is blocked and the conflict is explained Checklist - Submit a booking request for an event using its recorded requirements - Confirm the request is created as Pending and Venue Staff are notified - Confirm the venue calendar shows the period as Tentative - Confirm the event status moves from Approved to Planning on the first request - Be blocked from holding more than one pending request for the same event - Be blocked from requesting a venue already Pending or Confirmed for another event in that period - View the status of each of my booking requests | 3 | C-01, C-16, C-17, C-37, C-46, C-60, T-20, T-49
1 | E06 Venue Search & Booking | E06-S04 | Decide on a venue booking request | As a Venue Staff member, I want to approve or reject booking requests and record my reasoning so that Coordinators receive a clear, traceable decision. | Scenario 1 - Request approved and confirmed Given a booking request is pending and the venue is free for the period When I approve it Then the booking becomes Confirmed, the venue calendar is updated and the Coordinator is notified Scenario 2 - Rejected with reason and alternative Given I reject a request When I record a reason and optionally suggest an alternative venue Then the Coordinator is notified with both, and can amend the request to the suggested alternative without restarting the search Scenario 3 - Rejection without reason blocked Given I attempt to reject without recording a reason When I confirm Then the rejection is blocked Checklist - Approve a pending booking request for a free venue - Confirm the booking becomes Confirmed and the calendar updates - Reject a request with a recorded reason - Be blocked from rejecting without a reason - Suggest an alternative venue alongside a rejection - Confirm the Coordinator can amend the request to the suggested venue without starting a new search - Confirm the Coordinator is notified of either decision | 3 | C-08, T-39
1 | E06 Venue Search & Booking | E06-S05 | Hold a venue tentatively | As an Event Coordinator, I want to place a tentative hold on a venue so that it is not taken by another event while the arrangements are still being finalised. | Scenario 1 - Tentative hold placed Given a venue is free for the period When I place a tentative hold Then the calendar shows the period as Tentative and the hold is recorded against my event Scenario 2 - Slot already held or booked Given a venue already has a tentative hold or a confirmed booking for the period When I attempt to hold it for another event Then the hold is refused and the existing hold or booking is identified Scenario 3 - Hold becomes a booking request Given I hold a venue tentatively When I submit a booking request for that venue Then the hold becomes a pending booking request for the same period Scenario 4 - Hold released Given I hold a venue tentatively and no longer need it When I release the hold Then the period returns to Free on the calendar Checklist - Place a tentative hold on a venue that is free for the period - See the period shown as Tentative on the venue calendar - Be refused when the slot already has a tentative hold or a confirmed booking for another event - Convert a tentative hold into a booking request - Release a tentative hold, returning the period to Free - Confirm only one active hold or confirmed booking exists per venue and period | 3 | C-01, C-16, C-37, C-60, T-49
1 | E06 Venue Search & Booking | E06-S06 | Prevent double-booking of a venue | As a Venue Staff member, I want to be blocked from approving a booking that overlaps an existing confirmed booking for the same venue so that a venue is never committed to two events at once. | Scenario 1 - Overlapping approval blocked Given a venue has a confirmed booking When I attempt to approve another request overlapping that period Then approval is blocked and the conflicting booking is identified Scenario 2 - Competing request flagged Given two pending requests cover the same venue and overlapping times When I approve one of them Then the other is flagged as conflicting and cannot be approved until the conflict is resolved Scenario 3 - Simultaneous approval fails safely Given another Venue Staff member approves a conflicting request moments before me When my approval is processed Then it fails and I am told the venue has just been taken Checklist - Be blocked from approving a request overlapping an existing confirmed booking - See which existing booking is causing the conflict - Confirm a competing pending request is flagged as conflicting once one is approved - Confirm a simultaneous approval by another Venue Staff member fails safely - Be told the venue has been taken when a simultaneous approval wins - Confirm no venue ever holds two confirmed bookings over the same period | 5 | C-46, T-22
1 | E07 Equipment & Technical Support | E07-S01 | Maintain the equipment catalogue | As a Technical Support Staff member, I want to maintain equipment records including type, quantity, location and operational status so that availability checks are based on accurate data. | Scenario 1 - Item added and reservable Given I am adding an equipment item When I save its type, description, quantity, location and operational status Then it becomes available for reservation Scenario 2 - Quantity drop flags reservations Given an item is already reserved for upcoming events When I reduce its quantity below the amount reserved Then the affected reservations are flagged and the relevant Coordinators are notified Scenario 3 - Item retired Given an item has no future reservations When I retire it Then it no longer appears in availability checks and its past reservations are retained Checklist - Add an equipment item with type, description, quantity, location and operational status - Update any of those attributes on an existing item - Confirm a new item becomes available for reservation - Confirm affected reservations are flagged when quantity drops below the amount reserved - Retire an item that has no future reservations - Confirm retired items no longer appear in availability checks | 3 | -
1 | E07 Equipment & Technical Support | E07-S02 | Request equipment for an event | As an Event Coordinator, I want to record the equipment an event needs, with quantities, so that Technical Support Staff can check whether it can be provided. | Scenario 1 - Equipment recorded against an event Given I am planning an approved event When I add equipment items with quantities to an event Then the request is saved against the event and the Technical Support Staff are notified Scenario 2 - Request exceeds total stock Given I request more of an item than ConnectSphere owns in total When I save the request Then I am warned that the request cannot be met from existing stock Scenario 3 - Events independent of each other Given an event has several events When I record equipment for the event Then the other events are unaffected Checklist - Add equipment items with quantities to a specific event - Confirm the request is saved against the event and Technical Support Staff are notified - Be warned when requesting more than ConnectSphere owns in total - Record different equipment for different events of the same event - Amend or remove an equipment request before it is reserved | 3 | T-25
1 | E07 Equipment & Technical Support | E07-S03 | Check equipment availability | As a Technical Support Staff member, I want to see how much of an item is free for a given date and time so that I can decide whether a request can be met. | Scenario 1 - Reserved and faulty stock excluded Given some items are reserved for other events in the period When I check availability Then the free quantity excludes those reservations and any items marked damaged or under maintenance Scenario 2 - Location does not affect availability Given an item is free for the requested date and time but is currently located at another venue When I check availability Then it is shown as available and no transport allowance is applied Scenario 3 - Non-overlapping events share an item Given two events require the same item at non-overlapping times on the same day When I check availability Then the item is free for both Checklist - View the free quantity of an item for a given date and time - Confirm reservations for other events are excluded from the free quantity - Confirm damaged or under-maintenance items are excluded - Confirm items at other venues are still counted as available - Confirm the same item can serve two events at non-overlapping times | 5 | C-07, C-20
1 | E07 Equipment & Technical Support | E07-S04 | Reserve equipment for an event | As a Technical Support Staff member, I want to reserve equipment for an event so that limited equipment is not committed to two events at the same time. | Scenario 1 - Full reservation recorded Given sufficient equipment is free for the period When I reserve the requested quantity Then the reservation is recorded against the event and the Event Coordinator is notified Scenario 2 - Partial reservation and shortfall Given only part of the requested quantity is free When I record a partial reservation Then the Coordinator is notified of the shortfall and the outstanding quantity Scenario 3 - Fully committed item shows nothing free Given an item becomes fully committed When availability is next checked for that period Then no free quantity is shown Scenario 4 - Reservation released Given an event is cancelled or its equipment is no longer required When I release the reservation Then the quantity returns to the available pool Checklist - Select an event and equipment item to reserve - Specify the quantity required - See an error when the requested quantity exceeds what is available - Record a partial reservation and notify the Coordinator of the shortfall - Release a reservation when an event is cancelled or the equipment is no longer needed - Receive confirmation showing the event, date, time, item and quantity | 5 | C-21, T-24, B-09
1 | E07 Equipment & Technical Support | E07-S05 | Mark equipment as unavailable | As a Technical Support Staff member, I want to mark equipment as damaged or under maintenance so that it is not treated as available for events. | Scenario 1 - Item marked unavailable Given an item has no reservations in the period When I mark it unavailable with a reason and a period Then it is excluded from availability checks for that period Scenario 2 - Reserved item flags its events Given an item is reserved for an upcoming event When I mark it unavailable Then the affected events are flagged and their Coordinators are notified Checklist - Mark an item unavailable for a specified period with a recorded reason - Confirm it is excluded from availability checks for that period - Confirm affected events are flagged and Coordinators notified - Return an item to service, restoring it to availability checks | 1 | B-04
1 | E07 Equipment & Technical Support | E07-S06 | Request technical support for an event | As an Event Coordinator, I want to request on-site technical support for an event and describe what is needed so that suitable staff can be allocated. | Scenario 1 - Support request recorded Given an event requires technical support When I submit a request describing the support and the times it is needed Then the Technical Support Staff are notified and the request is recorded against the event Scenario 2 - Request accepted before venue confirmed Given the event does not yet have a confirmed venue When I submit a technical support request Then it is accepted and reviewed alongside venue identification Scenario 3 - Event marked as needing none Given an event needs no technical support When I mark it as such Then no request is created and confirmation is not blocked on staff assignment Checklist - Submit a technical support request against a specific event - Describe the support required and the times it is needed - Confirm Technical Support Staff are notified - Submit a request before the venue is confirmed - Mark an event as requiring no technical support | 1 | C-22, T-23
1 | E07 Equipment & Technical Support | E07-S07 | Assign and manage technical staff for an event | As a Technical Support Staff member, I want to assign and manage available colleagues to support an event so that the right people are on site at the right time. | Scenario 1 - Available colleague assigned Given an event has an open technical support request and a colleague is available for its times When I assign them Then they are notified and the assignment appears on their schedule Scenario 2 - Overlapping assignment blocked Given a colleague is already assigned to another event at an overlapping time When I try to assign them Then the assignment is blocked and the conflicting event is identified Scenario 3 - Assignment removed Given an assignment exists When I remove it Then the colleague is notified and the slot is freed Scenario 4 - Replacement assigned under same check Given I have removed an assignment When I assign a replacement Then the same conflict check is applied Checklist - Assign a colleague only when they have no conflicting assignment the event's period - See the assignment on the assigned staff member's schedule - Be blocked from assigning a colleague with an overlapping assignment, with the conflicting event identified - Remove an existing assignment - Assign a replacement colleague subject to the same conflict check - Confirm the staff member is notified when assigned or removed | 3 | C-39
1 | E08 Readiness & Confirmation | E08-S03 | Confirm an event | As an Event Coordinator, I want to confirm an event once the event's arrangements are complete so that the Event Organiser and Attendees can rely on the details. | Scenario 1 - All arrangements complete, event confirmed Given the event has a confirmed venue booking and its full requested equipment reserved When I confirm the event Then the status becomes Confirmed and the Event Organiser is notified with the confirmed details Scenario 2 - Missing venue blocks confirmation Given the event has no confirmed venue When I try to confirm Then confirmation is blocked and the outstanding items are listed Scenario 3 - Partial equipment blocks confirmation Given the event has only a partial equipment reservation When I try to confirm Then confirmation is blocked and the outstanding quantity is shown Scenario 4 - None required does not block Given the event was submitted with 'none required' for equipment When I confirm it Then that requirement counts as fulfilled and does not block confirmation Scenario 5 - Outstanding support assignment blocks confirmation Given the event requested technical support and no staff are assigned When I try to confirm Then confirmation is blocked Scenario 6 - Organiser sees confirmed arrangements Given an event has been confirmed When the Event Organiser views it Then the confirmed venue, date, time and arrangements are shown Checklist - Confirm an event that has a confirmed venue and full equipment reservation - Be blocked from confirming while the event lacks a venue - Be blocked from confirming while an equipment reservation is partial, with the shortfall shown - Confirm an event whose equipment requirement was recorded as 'none required' - Be blocked from confirming while a requested technical support assignment is outstanding - Confirm the Event Organiser is notified with the full confirmed details | 5 | C-13, C-39, C-59, C-63, T-02, T-24, T-27
1 | E08 Readiness & Confirmation | E08-S04 | Revert a confirmed event to planning | As an Event Coordinator, I want to return a confirmed event to planning when an arrangement breaks so that its status reflects reality. | Scenario 1 - Reverted with a recorded reason Given an event is Confirmed When I revert it to Planning and record a reason Then the status becomes Planning and the Event Organiser is notified with the reason Scenario 2 - Registered Attendees notified Given registered Attendees exist When the event is reverted Then they are notified that arrangements are being revised Scenario 3 - No automatic reversion Given an arrangement breaks on a confirmed event When no one reverts it Then the status stays Confirmed and the affected arrangement is flagged Checklist - Revert a confirmed event to Planning with a recorded reason - Confirm the Organiser is notified with the reason - Confirm registered Attendees are notified - Confirm the status never reverts automatically - Confirm the reversion is recorded in the activity log | 1 | C-48, T-03, T-28
1 | E08 Readiness & Confirmation | E08-S05 | Complete an event | As an Event Coordinator, I want an event to become Completed once it has taken place so that attendance can be recorded and the event closed. | Scenario 1 - Auto-completed after the end time Given an event is Confirmed and its end time has passed When the system next evaluates it Then the status becomes Completed Scenario 2 - Marked complete manually Given an event is Confirmed and has already started When I mark it complete Then the status becomes Completed Scenario 3 - Premature completion blocked Given an event is Confirmed and has not yet started When I try to mark it complete Then the action is blocked Scenario 4 - Cancelled event never auto-completes Given an event is Cancelled When its original end time passes Then it is not auto-completed and remains Cancelled Checklist - Confirm an event auto-completes once its end time has passed - Mark an event complete manually once it has started - Be blocked from marking an event complete before it has started - Confirm a cancelled event is never auto-completed - Confirm the transition is recorded in the activity log | 3 | T-03, T-26, T-48
1 | E09 Attendee Registration | E09-S01 | Register for an event | As an Attendee, I want to register for a confirmed event so that my place is reserved and I receive the event information. | Scenario 1 - Place reserved in an open event Given an event is Confirmed, registration is open and places remain When I submit the required registration information Then my place is reserved and I receive a confirmation containing the event details Scenario 2 - Duplicate registration prevented Given I have already registered for the event When I try to register again Then I am told I am already registered and no duplicate registration is created Scenario 3 - Missing fields identified Given a required registration field is empty When I submit Then registration is blocked and the missing fields are identified Scenario 4 - Unconfirmed event refused Given an event is not Confirmed When I attempt to register Then registration is refused Checklist - Register for a confirmed event - Provide name, email address and contact number as the required registration information - Receive a confirmation containing the event details - Be told I am already registered rather than creating a duplicate - Be blocked with missing fields identified when required information is absent - Be refused registration for an event that is not Confirmed | 5 | C-35, T-48
1 | E09 Attendee Registration | E09-S02 | Enforce registration capacity | As an Event Organiser, I want registration to stop at the booked venue's capacity so that more people do not register than the venue can hold. | Scenario 1 - Venue capacity enforced Given the event's capacity is the booked venue's capacity When registrations reach that number Then further registrations are refused Scenario 2 - Simultaneous final registration Given one place remains When two Attendees submit registrations at the same moment Then only one succeeds and the other is told the event is full Scenario 3 - Full event offers the waiting list Given the event is full When an Attendee opens the registration page Then registration is closed and the waiting list is offered where it is enabled Scenario 4 - VIP added beyond normal registration Given normal registration is full and total registrations remain below the booked venue's capacity When the Event Coordinator adds a VIP attendee manually Then the registration is created and recorded as a manual addition Scenario 5 - VIP blocked at venue capacity Given total registrations already equal the booked venue's capacity When the Event Coordinator attempts to add a VIP manually Then the addition is blocked Checklist - Confirm registration is refused once the booked venue's capacity is reached - Confirm a simultaneous final registration is handled without over-booking - Confirm the waiting list is offered when the event is full and the list is enabled - Add a VIP attendee manually when normal registration is full - Be blocked from adding a VIP once total registrations equal venue capacity - Confirm a manual addition is distinguishable from a normal registration | 3 | C-05, C-58, T-30, T-31, T-50, B-11
1 | E09 Attendee Registration | E09-S03 | Control the registration period | As an Event Organiser, I want to set when registration opens and closes, and when withdrawal closes, so that Attendees can act only during the permitted windows. | Scenario 1 - Before registration opens Given the registration opening date has not been reached When an Attendee views the event Then registration is shown as not yet open and the opening date is stated Scenario 2 - After registration closes Given the registration closing date has passed When an Attendee tries to register Then registration is refused Scenario 3 - Closing date after event start warned Given I set a closing date that falls after the event has started When I save Then I am warned and asked to confirm this is intended Scenario 4 - Waiting list enabled Given I enable the waiting list for an event When an event becomes full Then Attendees are offered the waiting list Checklist - Set registration opening and closing dates - Set a withdrawal deadline - Enable or disable the waiting list for the event - Confirm registration is refused outside the permitted window - Confirm the opening date is shown to Attendees before registration opens - Be warned when setting a closing date after the event has started | 3 | C-24, C-44, T-42
1 | E09 Attendee Registration | E09-S04 | Join the waiting list | As an Attendee, I want to join the waiting list when an event is full so that I can still attend if a place is released. | Scenario 1 - Joined a full event's list Given an event is full and the waiting list is enabled When I join the waiting list Then I am added and told I will be notified when a place is released Scenario 2 - Released place notified to all Given a place is released in an event with a waiting list When the place becomes available Then all waitlisted Attendees are notified and the place is claimed on a first-come, first-served basis Scenario 3 - Claimed place leaves the list Given I claim a released place When my registration completes Then I am removed from the waiting list Scenario 4 - Disabled list offers nothing Given the waiting list is disabled for an event When the event is full Then no waiting list is offered Checklist - Join the waiting list for a full event where the list is enabled - See confirmation that I have joined - Receive a notification when a place is released - Claim a released place on a first-come, first-served basis - Leave the waiting list - Confirm no waiting list is offered when the Organiser has disabled it | 5 | C-23, T-33, T-46, B-10
1 | E09 Attendee Registration | E09-S05 | Withdraw my registration | As an Attendee, I want to withdraw my registration so that my place is released to someone else. | Scenario 1 - Registration withdrawn Given I am registered and the withdrawal deadline has not passed When I withdraw Then my registration is cancelled and the place becomes available again Scenario 2 - Withdrawal after deadline refused Given the withdrawal deadline has passed When I try to withdraw Then I am told withdrawal has closed and given a contact for assistance Checklist - Withdraw my registration before the deadline - Confirm the released place becomes available again - Be refused after the withdrawal deadline, with a contact provided | 3 | C-24, T-48, B-10
1 | E09 Attendee Registration | E09-S06 | Record attendance | As an Event Coordinator, I want to record which registered Attendees actually attended the event so that registration and attendance can be distinguished. | Scenario 1 - Attendance marked after completion Given an event has status Completed When I mark an Attendee as attended for an event Then their record shows attended and the registration figure is unchanged Scenario 2 - Registered but not attended Given a registered Attendee did not attend When the event is Completed Then they are shown as registered but not attended Scenario 3 - Recording before completion blocked Given an event is not yet Completed When I try to record attendance Then the action is blocked Checklist - Mark a registered Attendee as attended for a specific event - Confirm the registration figure is unchanged by attendance recording - See Attendees who registered but did not attend distinguished from those who did - Be blocked from recording attendance before the event is Completed - View registration and attendance counts side by side for the event | 3 | C-45
1 | E09 Attendee Registration | E09-S07 | View registrations for my event | As an Event Organiser, I want to view the list of Attendees registered for my event so that I can plan for the numbers attending the event. | Scenario 1 - Registrations grouped by event Given Attendees have registered for my event When I open its registration list Then I see each Attendee's name, email address and contact number Scenario 2 - Counts and remaining capacity Given I open the registration list When it is displayed Then the registered count and remaining capacity are shown for the event Scenario 3 - Unmanaged event refused Given an event does not belong to my client organisation When I attempt to open its registration list Then access is refused Scenario 4 - Waitlist shown separately Given a waiting list exists for an event When I view the list Then waitlisted Attendees are shown separately from registered Attendees Checklist - View registered Attendees for an event I manage, grouped by event - See each Attendee's name, email address and contact number, and no other personal data - See registered count and remaining capacity for the event - See waitlisted Attendees separately from registered ones - Be refused access to registration lists for events I do not manage | 1 | C-26, T-32, O-05
1 | E10 Changes, Rescheduling & Cancellation | E10-S01 | Request a change after submission | As an Event Organiser, I want to request a change to my event after it has been submitted or confirmed so that the arrangements reflect what I now need. | Scenario 1 - Change request recorded Given my event has been approved or confirmed When I submit a change request describing what should change Then the assigned Coordinator is notified and the request is recorded against the event Scenario 2 - Confirmed details shown alongside Given a change request is pending When I view my event Then the currently confirmed details are still shown alongside the pending request Scenario 3 - Refused edit offers the form Given I attempt to edit a restricted field directly after approval When the edit is refused Then I am offered the change request form pre-filled with that field Scenario 4 - Approved change applied Given the Coordinator approves my change request When it is applied Then the event is updated and I am notified Checklist - Submit a change request against an approved or confirmed event - Describe the change requested - Confirm the assigned Coordinator is notified - See currently confirmed details alongside any pending request - Reach the change request form when a restricted direct edit is refused - Be notified when the Coordinator approves or declines the request | 3 | C-14, C-52, C-54, T-16
1 | E10 Changes, Rescheduling & Cancellation | E10-S02 | Distinguish minor edits from arrangement-affecting changes | As an Event Coordinator, I want the system to tell me when a change affects arrangements already confirmed so that I re-check them rather than assuming they still hold. | Scenario 1 - Attendance beyond capacity flagged Given an event has a confirmed venue When its expected attendance is increased beyond that venue's capacity Then the venue booking is flagged for review and the Venue Staff are notified Scenario 2 - Description-only edit flags nothing Given an event has a confirmed venue and equipment When only the event description is edited Then no arrangements are flagged Scenario 3 - Affected arrangements shown first Given a change affects confirmed arrangements When I save it Then I am shown which arrangements are affected before the change takes effect Scenario 4 - Over-subscription warns only Given a venue change reduces the event's capacity below its registration count When the change is saved Then I am warned and shown the over-subscription, and no Attendee is automatically removed or waitlisted Scenario 5 - Date change flags venue and equipment Given the event's date or time changes When the change takes effect Then its venue booking and equipment reservations are flagged as requiring reconfirmation Checklist - Confirm attendance increases beyond venue capacity flag the booking for review - Confirm description-only edits flag nothing - See which arrangements are affected before a change takes effect - Confirm over-subscription warns the Coordinator without removing Attendees - Confirm date or time changes flag both venue and equipment for reconfirmation - Confirm affected Venue Staff and Technical Support Staff are notified | 5 | C-05, T-16, B-05, B-11
1 | E10 Changes, Rescheduling & Cancellation | E10-S04 | Cancel an event | As an Event Coordinator, I want to cancel an event and release its arrangements so that venues and equipment do not stay committed to something that will not happen. | Scenario 1 - Event cancelled, arrangements released Given an Event Organiser requests cancellation When I cancel the event and record a reason Then its status becomes Cancelled, its venue booking and equipment reservations are released, the venue calendar is updated and the affected staff are notified Scenario 2 - Attendees and waitlist notified Given Attendees are registered or waitlisted for a cancelled event When the cancellation completes Then all of them are notified Scenario 3 - Cancelled event read-only Given an event has been cancelled When any user views it Then it is read-only and shows the cancellation reason and date Scenario 4 - Organiser cancellation becomes a request Given an Event Organiser attempts to cancel directly When they submit Then the action is recorded as a cancellation request for the Coordinator to action Checklist - Cancel an event, releasing its venue and equipment - Record a reason for the cancellation - Confirm the released venue becomes available again on the calendar - Confirm released equipment returns to the available pool - Confirm registered and waitlisted Attendees are notified - Confirm a cancelled event is read-only and shows its reason and date | 5 | C-14, C-54, T-07, T-48
1 | E11 Notifications & Reminders | E11-S01 | Notify users about events they are involved in | As a user involved in an event, I want to be notified when its status or arrangements change so that I do not have to keep checking the system and nobody continues working from outdated information. | Scenario 1 - Status change notified Given I am linked to an event When its status changes or a booking decision is made Then I receive a notification stating what changed, when, and which event it concerns Scenario 2 - All affected parties notified Given the event's date, time or venue changes When the change takes effect Then the Event Organiser, assigned Venue Staff, assigned Technical Support Staff and registered Attendees are all notified Scenario 3 - Unaffected users not notified Given a change does not affect a particular user's responsibilities When the change occurs Then that user is not notified Scenario 4 - Delivered in-app and by email Given a notification is generated for me When it is delivered Then it appears in the system and is also sent to my registered email address Scenario 5 - Unread notifications distinguished Given I have several unread notifications When I open my notification list Then they are shown newest first with unread ones distinguished Scenario 6 - Marked as read Given I open an unread notification When I have read it Then it is marked as read Checklist - Receive a notification when an event I am linked to changes status - Receive a notification when a booking decision is made - Confirm all affected parties are notified when the event's date, time or venue changes - Confirm users whose responsibilities are unaffected are not notified - See what changed, when, and which event and event it concerns - Receive the same notification in the system and by email - See notifications newest first with unread ones distinguished - Mark a notification as read | 5 | C-04, C-29, C-53, T-35, T-36, T-44, T-48
1 | E14 Audit & History | E14-S02 | Record significant actions in an activity log | As a ConnectSphere staff member, I want significant actions to be recorded so that we can determine who did what and when. | Scenario 1 - Status change recorded Given an event status changes When the change completes Then an entry is recorded with the actor, the action, the affected event and the time Scenario 2 - Access denial recorded Given a user is denied access to an event or screen When the refusal occurs Then an entry is recorded with the user, the target and the time Scenario 3 - Booking decision recorded Given a venue booking is approved, rejected or released When the action completes Then an entry is recorded with the actor, the action, the affected records and the time Scenario 4 - Deactivation recorded Given an account is deactivated When the action completes Then an entry is recorded Scenario 5 - Log entries immutable Given an activity log entry exists When any user attempts to edit or delete it Then the attempt is refused Checklist - Record every event status change with actor, action, event and time - Record every denied access attempt with user, target and time - Record every venue booking approval, rejection and release - Record every account deactivation - Confirm log entries cannot be edited or deleted by any user | 3 | T-04
2 | E01 Access & Identity | E01-S05 | Set my notification preferences | As an Event Coordinator, I want to choose which notifications I receive and through which channel so that I am not overwhelmed by messages that do not concern me. | Scenario 1 - Category switched off Given I am signed in When I turn off a notification category and save Then I no longer receive notifications in that category Scenario 2 - Mandatory category cannot be disabled Given a notification category is designated by ConnectSphere as mandatory When I open my preferences Then that category is shown as always on and cannot be turned off | 3 | C-29
2 | E01 Access & Identity | E01-S06 | Maintain client organisation records | As an Event Coordinator, I want to create and update client organisation records so that several Event Organisers from the same client are linked to one organisation. | Scenario 1 - Organisation created Given I am creating a client organisation When I save it with the required details Then it becomes available for selection when linking Event Organisers and events Scenario 2 - Duplicate name warned Given an organisation with the same registered name already exists When I try to save a duplicate Then I am warned and offered the option to link to the existing record instead | 3 | -
2 | E01 Access & Identity | E01-S07 | View a client's event history | As an Event Coordinator, I want to view all past and upcoming events for a client organisation so that I can prepare for a new request with that client's history in mind. | Scenario 1 - Past and upcoming shown Given a client organisation has past and upcoming events When I open its record Then both lists are shown with dates and current statuses Scenario 2 - Empty state, not an error Given a client organisation has no events yet When I open its record Then an empty state is shown rather than an error | 1 | -
2 | E01 Access & Identity | E01-S09 | Switch between my roles | As a user who holds more than one role, I want to switch my active role so that I can act on the tasks belonging to each role without a separate account for each. | Scenario 1 - Active role switched Given I hold more than one role and my active role is Venue Staff When I switch to Technical Support Staff Then I see only the tasks and events permitted to that role and my active role is displayed Scenario 2 - Action outside active role refused Given my active role is Technical Support Staff When I attempt an action permitted only to Venue Staff Then the action is refused Scenario 3 - No switcher for a single role Given I hold exactly one role When I sign in Then no role switcher is shown Scenario 4 - Role persists across screens Given I have switched my active role When I move to another part of the system Then my active role remains unchanged until I switch again or sign out Scenario 5 - Last used role on sign-in Given I hold more than one role When I sign in Then my active role is set to the role I last used | 5 | C-33, T-10
2 | E02 Event Request & Submission | E02-S04 | Classify an event by category | As an Event Coordinator, I want to assign a category to an event from a predefined list so that events are classified to support filtering and reporting. | Scenario 1 - Category saved Given I am creating or editing an event When I select a category from ConnectSphere's list Then it is saved against the event Scenario 2 - New category available Given ConnectSphere adds a new category When I next create an event Then the new category is available for selection | 1 | C-32, O-13
2 | E02 Event Request & Submission | E02-S05 | Reuse a previous event's details | As an Event Organiser, I want to create a new request by copying a previous event so that I do not re-enter the same information for a recurring event. | Scenario 1 - Previous event copied Given I have a previous event When I choose to copy it Then a new draft is created with the requirements copied and the dates left blank Scenario 2 - Missing reference flagged Given the copied event referenced a venue or equipment item that no longer exists When the draft is created Then that requirement is flagged for review rather than copied silently | 3 | -
2 | E02 Event Request & Submission | E02-S06 | Attach supporting documents | As an Event Organiser, I want to attach documents such as floor plans and programmes to my event so that ConnectSphere has the materials it needs. | Scenario 1 - Permitted file attached Given I am viewing an event I own When I upload a PDF, PNG or JPEG of 300MB or less Then it is attached to the event and visible to the assigned internal users Scenario 2 - Oversized or wrong type rejected Given I upload a file larger than 300MB or of a type other than PDF, PNG or JPEG When I confirm the upload Then it is rejected and the permitted types and size limit are stated Scenario 3 - Attachment deleted Given a document is attached to an event When I delete it Then it is removed and the deletion is recorded in the activity log Checklist - Attach a PDF, PNG or JPEG of 300MB or less to an event I own - Be rejected with the permitted types and limit stated when the file is too large or the wrong type - See attached documents as an assigned internal user - Delete an attachment, with the deletion recorded in the activity log | 3 | C-31, T-40, O-08
2 | E04 Programme & Sessions | E04-S01 | Record the event programme | As an Event Organiser, I want to record the programme for my event, including sessions and breaks, so that ConnectSphere can plan the venue and support around it. | Scenario 1 - Programme item added Given I am editing my event When I add a programme item with a title, start time and end time Then it appears in the event in chronological order Scenario 2 - Item outside event times warned Given a programme item falls outside the event's own start and end times When I save it Then I am warned and asked either to correct the times or extend the event Scenario 3 - Overlapping items warned Given two programme items overlap When I save them Then I am warned of the overlap | 5 | T-19
2 | E04 Programme & Sessions | E04-S02 | Create a multi-session event | As an Event Organiser, I want to define an event made up of one or more sessions so that each session's requirements can be planned separately. | Scenario 1 - Sessions hold their own requirements Given I am creating an event When I add sessions Then each session stores its own date, time, expected attendance, venue requirements and equipment requirements Scenario 2 - Single-session event needs no structure Given my event has a single session When I create it Then no additional structure is required and the event behaves as a single-session event Scenario 3 - Suitability judged per session Given two sessions of my event have different expected attendance When a venue search is run for each Then suitability is assessed against that session's own attendance and requirements Scenario 4 - Deleted session releases its booking Given a session has a confirmed venue booking When I delete that session Then the booking is released, the Venue Staff are notified, and the deletion is recorded in the activity log Checklist - Add one or more sessions, each with its own date, time, attendance and requirements - Create a single-session event without extra steps - Edit a session's date, time or requirements before its booking is confirmed - Delete a session, releasing any confirmed booking and notifying Venue Staff - See each session listed with its own venue booking and equipment status | 5 | C-19, C-62, T-48
2 | E05 Venue Catalogue & Availability | E05-S05 | Apply setup and turnaround time | As a Venue Staff member, I want to record the setup and turnaround time each venue requires so that consecutive bookings leave enough time for preparation and reset. | Scenario 1 - Availability extended by turnaround Given a venue has a defined setup and turnaround time When its availability is calculated Then the unavailable period extends before and after the published event times Scenario 2 - Insufficient turnaround flagged Given a booking request would leave less than the required turnaround after an existing booking When the request is submitted Then it is flagged as conflicting | 5 | C-18, C-38
2 | E08 Readiness & Confirmation | E08-S01 | View readiness of an event | As an Event Coordinator, I want to see whether venue, equipment and technical support are ready so that I know what still needs my attention. | Scenario 1 - Arrangement states shown Given an event is in planning When I open its readiness view Then each arrangement is shown as complete, in progress or not started Scenario 2 - Responsible role identified Given an arrangement is not started When I view it Then the responsible role and the action required are shown | 3 | -
2 | E08 Readiness & Confirmation | E08-S02 | Track outstanding actions across events | As an Event Coordinator, I want a list of upcoming events with incomplete arrangements so that nothing is overlooked before an event takes place. | Scenario 1 - Incomplete events listed by date Given I have upcoming events with incomplete arrangements When I open my outstanding actions list Then those events are listed with the specific incomplete items, ordered by event date Scenario 2 - Approaching event highlighted Given an event is close to its date and arrangements are still incomplete When I view the list Then that event is highlighted as urgent | 3 | C-28
2 | E10 Changes, Rescheduling & Cancellation | E10-S03 | Reschedule an event | As an Event Coordinator, I want to reschedule an event to new dates so that it can still take place when the original dates no longer work. | Scenario 1 - Date change flags bookings Given an event has a confirmed venue and equipment When I change its date Then the existing bookings are flagged as requiring reconfirmation and are not moved silently Scenario 2 - Registered Attendees notified Given Attendees have registered for the event When it is rescheduled Then all registered Attendees are notified of the new date and time | 5 | C-25, O-18
2 | E10 Changes, Rescheduling & Cancellation | E10-S05 | Handle a venue lost from a confirmed event | As an Event Coordinator, I want to be alerted when a venue becomes unavailable for one of my confirmed events so that I can arrange an alternative before Attendees are affected. | Scenario 1 - Blocked venue flags the event Given my event has a confirmed venue When Venue Staff block that venue over the event's period Then I am notified and the event is flagged as at risk Scenario 2 - At-risk event offers a new search Given my event is flagged as at risk When I open it Then the reason and the affected arrangement are shown and I can begin a new venue search from that screen | 3 | -
2 | E11 Notifications & Reminders | E11-S03 | Receive reminders about upcoming commitments | As a Technical Support Staff member, I want reminders about upcoming events I am supporting so that equipment and support are prepared in time. | Scenario 1 - Reminder lists requirements Given I am assigned to an upcoming event When the reminder point before it is reached Then I receive a reminder listing the equipment and support required Scenario 2 - Cancelled event sends none Given an event is cancelled before its reminder is due When the reminder point is reached Then no reminder is sent | 3 | C-28, O-11
2 | E11 Notifications & Reminders | E11-S04 | Alert on incomplete arrangements | As an Event Coordinator, I want to be alerted when an upcoming event still has incomplete arrangements so that I can act while there is still time. | Scenario 1 - Incomplete items named Given an upcoming event has an incomplete essential arrangement When the alert point before it is reached Then I receive an alert naming the incomplete items Scenario 2 - No alert when complete Given all arrangements are completed before the alert point When the alert point is reached Then no alert is sent | 3 | -
2 | E12 Calendar, Search & Dashboards | E12-S01 | View my events in a calendar | As an Event Coordinator, I want to see my events in a calendar so that I can plan my workload across the coming weeks. | Scenario 1 - Events shown on their dates Given I have events spread across several weeks When I open the calendar Then my events appear on their dates with their status indicated Scenario 2 - Multi-day event spans its days Given an event spans several days When I view the calendar Then it is shown across all its days rather than only the first | 3 | -
2 | E12 Calendar, Search & Dashboards | E12-S02 | Search and filter events | As an Event Coordinator, I want to search events by name, client, date, venue, status, category or assigned Coordinator so that I can find a specific event quickly. | Scenario 1 - Permitted matches returned Given events match my criteria When I search Then only matching events that I am permitted to see are returned Scenario 2 - Empty result offers relaxation Given no events match my criteria When I search Then an empty result is shown with the option to relax the filters Scenario 3 - Filters combine Given I apply several filters at once When I search Then all the filters are applied together | 3 | -
2 | E12 Calendar, Search & Dashboards | E12-S03 | See my work on a role-based dashboard | As a Venue Staff member, I want a dashboard showing booking requests awaiting my decision and upcoming venue preparations so that I can see my outstanding work in one place. | Scenario 1 - Pending decisions listed Given booking requests are pending my decision When I open my dashboard Then they are listed with event name, venue, dates and how long each has been waiting Scenario 2 - Empty state, not an error Given I have no outstanding items When I open my dashboard Then an empty state is shown rather than an error | 5 | -
2 | E12 Calendar, Search & Dashboards | E12-S04 | Use the system on a mobile device | As a Venue Staff member, I want to use the system on my phone while preparing a venue so that I can check and update arrangements without returning to a desk. | Scenario 1 - Readable without horizontal scrolling Given I open the system on a mobile device When I view my dashboard, an event or a venue calendar Then the content is readable and usable without horizontal scrolling Scenario 2 - Mobile update saves identically Given I am working on a mobile device When I update a preparation status Then the update is saved exactly as it would be on a desktop | 3 | -
2 | E13 Reporting & Export | E13-S01 | Generate an event report | As an Event Coordinator, I want to generate a summary report for an event so that I can share the arrangements at operational meetings. | Checklist - Generate a downloadable report containing event name, date and time, venue, equipment list, assigned technical support and total registered Attendees - Show aggregate attendee counts rather than personal data - Show incomplete arrangements with an Outstanding tag rather than omitting the section - Show a clear error with a retry option if generation fails | 5 | C-27, O-01
2 | E13 Reporting & Export | E13-S02 | Review venue usage over a period | As a Venue Staff member, I want to review venue bookings and usage over a chosen period so that I can plan maintenance and identify under-used spaces. | Checklist - Select a custom date range with start and end dates - Be rejected with a validation message when the start date is after the end date - See a breakdown per venue of total booked hours, total blocked hours and number of events - See blocked time in a column distinct from bookings - See an informative empty state when no records match | 5 | C-27, O-01
2 | E13 Reporting & Export | E13-S03 | Export attendee registration information | As an Event Organiser, I want to export the registration list for my event so that I can prepare badges and catering numbers. | Checklist - Export registrations only for events the Organiser manages - Generate a downloadable file of the registration list - Exclude sensitive personal data from the generated file | 3 | C-26, T-32
2 | E14 Audit & History | E14-S01 | View an event's change history | As an Event Coordinator, I want to see how an event's important information has changed over time so that I can explain how the current arrangements were reached. | Scenario 1 - Before and after values listed Given an event's date, venue, attendance or status has changed When I open its change history Then each change is listed with the previous value, the new value, who made it and when Scenario 2 - Restricted entries hidden Given I am not permitted to view a particular change When I open the history Then that entry is not shown to me | 3 | -

## SPRINT SUMMARY
Sprint | Stories | Points | Cumulative | Notes | Story Points
Sprint 1 | 12 | 36 | 36 | Deliberately the lightest. First sprint; the project instructions allow an initial sprint to be rough given evidence of reflection. | 1
Sprint 2 | 10 | 36 | 72 | Carries the notification enabler (E11-S01), which roughly fifteen later stories depend on. | 3
Sprint 3 | 13 | 43 | 115 | Venue booking and the whole of equipment and technical support, ending with confirmation. | 5
Sprint 4 | 12 | 40 | 155 | Registration, changes and cancellation. The showcase sprint. | 8
Total | 47 | 155
Counts and points are calculated from RELEASE 1 BACKLOG and update when it changes. The size-to-points mapping is a team decision (BDR T-37), not a customer requirement.

## CORE FEATURES BUILT
No. | Core feature | Delivered by | Stories
1 | User Authorisation and Authentication | E01-S01, E01-S02, E01-S03, E01-S08, E01-S11 | 5
2 | Event Request Creation | E02-S01, E02-S03 | 2
3 | Draft Event Requests | E02-S02 | 1
4 | Event Review and Approval | E03-S02, E03-S03 | 2
5 | Coordinator Assignment | E03-S01 | 1
6 | Event Status Management | E03-S05, E08-S03, E08-S04, E08-S05 | 4
7 | Event Information Management | E03-S07, E10-S02 | 2
8 | Venue Catalogue | E05-S01, E05-S02 | 2
9 | Venue Availability Calendar | E05-S03, E05-S04 | 2
10 | Venue Search and Filtering | E06-S01 | 1
11 | Venue Suitability Checking | E06-S02 | 1
12 | Venue Booking Request | E06-S03 | 1
13 | Venue Booking Approval | E06-S04 | 1
14 | Booking Conflict Detection | E06-S06 | 1
15 | Equipment Request Management | E07-S02 | 1
16 | Equipment Availability Checking | E07-S01, E07-S03, E07-S05 | 3
17 | Equipment Reservation | E07-S04 | 1
18 | Attendee Registration | E09-S01, E09-S05, E09-S07 | 3
19 | Event Change Requests | E10-S01, E10-S02 | 2
20 | Notification System | E11-S01 | 1